## Risk Assessment Form Spinner
Risk Assessment Form
Before
Date of Assessment |  | Friday 12th June
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Dryer
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager
Ranjan |  | Operations Manager
Szymon |  | Engineer
Sean |  | Engineer
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | High Care | Electrical | Dryer does not have reset button and is 415 volt, 3 phase |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Install a magnetic contactor or a No-Volt Release (NVR) switch. This ensures that if power is lost or an E-stop is pressed, the machine cannot automatically restart when power is restored until a manual reset button is pressed. | Szymon
2 | High Care | Electrical | Electrical box not IP rated, water can get into the electrical box cause electrical damage |  | Major | Possible | H18 | No control | Major | Possible | H18 | Upgrade the electrical enclosure to an appropriate IP rating (minimum IP56, preferably IP66 if subject to washdowns or heavy splashing). Ensure all cable entries use IP-rated glands. Install a residual current device (RCD) or earth leakage circuit breaker upstream to instantly cut power if a fault occurs. | Szymon
3 | High Care | Electrical | Isolator switch is made from cheap plastic could break easily |  | Minor | Unlikely | L5 | Isotation switch installed on machine | Minor | Unlikely | L5 | Replace the plastic switch with a heavy-duty, industrial-grade metal or impact-resistant polycarbonate isolator switch rated for the machine's load | Szymon
4 | High Care | Electrical | All buttons on the machine are not water proof & could cause water damage to the machine |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Sealed the display buttons | Szymon
5 | High Care | Crushing | Gas struts on the lifter does not soft close & could cause fractured fingers if operators do not keep fingers clear |  | Serious | Likely | H17 | Pinch Point warning decals near the hinge Gas strut on the machine | Serious | Likely | H17 | Replace existing struts with damped/soft-close gas struts or mechanical speed-restricting dampers. Install mechanical safety catch pins or a secondary locking latch to hold the lid securely open during loading/unloading. | Szymon
6 | High Care | Entanglement | No break on machine, when door is lifted the basket within still spins rapidly |  | Major | Possible | H18 | No control | Major | Possible | H18 | Adjust the motor on the break, this will slow the basket down. | Szymon
7 | High Care | Electrical | No safety interlock switch on the lid |  | Major | Possible | H18 | There is a safety switch on the lid but this was not set up correctly, buttons to adjust this is on the main display & can be changed by an operator, Safety switch is not austlian standard rated | Serious | Possible | M13 | Install a safety switch on the lid for australian rating | Szymon
8 | High Care | Struck by / Against | Accessing the inside of the tumbler, could hit head on the lid |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Conduct training with operator against the SOP | Jen
9 | High Care | Sharp Edge/Impliment | Sharp edges on the lid of the machine |  | Minor | Possible | M8 | No control | Minor | Possible | M8 | De-burr, grind down, and radius all sharp sheet metal edges. | Szymon

## Sleeving Environment
Risk Assessment Form
Before
Date of Assessment |  | 2026-08-18
Department |  | Sleeving | [5 empty] | Risk Matrix
Process / Machine |  | Environment
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager
Ranjan |  | Operations Manager
Szymon |  | Engineer
Sean |  | Engineer
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | Sleeving | Manual handling | twisting of the body when palletizing and changing tapae in machine, colleague may hit the the pole, |  | Serious | Likely | H17 | Manual handling training Exercises TL to help direct correct movements, 30 minutes rotation each colleague | Serious | Likely | H17
2 | Sleeving | Struck by / Against | limited space When pulling out pallet from cobot risk in colleague can hit by safety gate and manual pallet jack between line 2 and line 3 |  | Major | Likely | E21 | collegues need to move out from from line 2 |  |  |  | swwap the location where the colleague can pack the meals in line2 Pallet Jack training or refresher training | maintenance/ Mercy/Arlene
3 | Sleeving | Trip | tripping hazard due to limited spacing in between line 7, line 3 and line2 in palletizing |  | Major | Almost Certain | E23 | Nil | Major | Almost Certain | E23 | paint the floor for pallet location | maintenance
4 | Sleeving | Trip | when bringing sleeves in sleeving, pallets could pose a risk of trip with colleague carrying the boxes and not seeing the corner of the pallets |  | Major | Almost Certain | E23 | Nil | Major | Almost Certain | E23 | cut the roller conveyor in smaller length | maintenance
5 | Sleeving | Manual handling | When colleagues are palletizing product from the roller conveyor to the pallets, the are having to turn their bodies, 90 degrees that could cause muscel strain,Twisting incorrectly, muscle strains |  | Serious | Likely | H17 | Manual handling training Exercises TL to help direct correct movements, 30 minutes rotation each colleague
6 | sleeving | Struck by / Against | New line 13 end of line , risk of forklift vs pedestrain crash. Processing will be inside forklift operating area. |  | Serious | Likely | H17 | Can we move mezzaine? implementing new forklift vs pedestrain process, stop line 13 and allow forklift to perform mezzaine task and open once forklift is back to its operating area. | Major | Almost Certain | E23 | Can we shut mezzaine and open new on other side, can we move pallet wrap behind line 5 hmps.
7 | Sleeving | Crushing | new colleagues unknown about pinch points within new line |  | Serious | Possible | M13 | Nil | Major | Likely | E21 | Need to write SOP of all new machines & equipment installed installed
8 | Sleeving | Fatigue | Congestion, affects traffic flow, creating physical pressures on body parts while moving pallets, operating pallets jacks and collecting packaging pallets. |  | Extreme | Almost Certain | E25 | Nil | Major | Likely | E21 | Move auto pallet wrap behind line 5 and create more space.
9 | Sleeving | Ergonomic | Pushing pallets to new pallet wrapping area.While pushing pallets from line 1,2,7&6 colleague might have sore hand and back due to distance being longer to pallet wrap now |  | Major | Likely | E21 | Nil | Major | Possible | H18 | Closing mezz and moving back pallet wrapper bit behind further only near airbridge.
10 | Sleeving | Entanglement | line 13 Conveyer moving parts. |  | Major | Likely | E21 | nil | Major | Likely | E21 | Ensure guards are fitted and effective, keep access to moving parts restricted .
11 | Sleeving | Electrical | coiled cable bundles underneat conveyers on line 13 |  | Serious | Possible | M13 | Nil | Serious | Possible | M13 | Mount cable trays along conveyer frame. Line 6 is infront and walkway in between line 6 &13.
12 | Sleeving | Environmental | Floor scale marking |  | Serious | Possible | M13 | Nil | Minor | Possible | M8 | Apply high visibility hazard paint around the perimeter of the floor scale to make it raised clear to pedestrains.
13 | Sleeving | Environmental | Improper Staging, pallets are stored randomly on floor |  | Major | Likely | E21 | Order only required boxes, packaging are not allowed to drop extra packaging around floor and stage extra pallets returned in case of rollover and breakdowns. | Major | Likely | E21 | Build a process or sign a communication sheet so colleague follow strict rules on staging pallets. | Ben/Arlene/Birendra
Sleeving
Sleeving
Sleeving
Sleeving
Sleeving
| Sleeving Line 1 | Struck by / Against | Colleagues moving pallets in/out could be struck by falling cartons from MEZ |  | Major | Unlikely | M14 | Mesh guarding Pedsestrian / forklift zoning with safety barriers & training | Major | Unlikely | M14
| Sleeving Line 1 | Slip | Colleagues only have 1 opening between line 6 & line 1, this congests the area & could cause people to slip trip fall |  | Minor | Possible | M8 | Barrier | Minor | Possible | M8
| Sleeving Line 6 | Slip | Line 6 colleagues working in congested area with line 13 next to the area & requires a pallet of cardboard boxes next to the line, when a pallet for finished goods are being made, there is no way of pallets coming in/out of line 6 to for fill the cardboard boxes |  | Minor | Possible | M8 | NIl | Minor | Possible | M8
| Sleeving Line 6 | Inrush (Water/Mud/Other) | When colleagues are rushing could pose trip hazards working in the congested area |  | Minor | Possible | M8 | NIl | Minor | Possible | M8
| Walkway to sleeving | Struck by / Against | Barriers have been moved to allow for line 13, colleagues walking in the area could hit their bodies on line 13 machinery within the walk way |  | Minor | Possible | M8 |  | Minor | Possible | M8 | Barriers coming in
| Walkway to sleeving | Struck by / Against | Emergency exit door exiting from line 6 HRA to sleeving when opened will now block the walk way within sleeving |  | Minor | Unlikely | L5 | Signage Do Not Block | Minor | Unlikely | L5
| Sleeving Line 2 | Struck by / Against | Colleagues packing meals within the cartons of line 2 could be struck by pallets outgoing from line 3 & 7 due to the space avaliable |  | Serious | Likely | H17 |  | Serious | Likely | H17 | Move the packing side to be on line 1 side to remove the people from the area
| Sleeving Line 2 | Slip | Colleagues on line 2 could slip, trip, fall due to the congestion of the area |  | Serious | Likely | H17 |  | Serious | Likely | H17
| Sleeving Line 7 | Slip | Colleagues on line 7 could slip, trip, fall due to the congestion of the area, |  | Serious | Likely | H17 |  | Serious | Likely | H17
| Sleeving Line 7 | Slip | When the Co-Bot stops working operators require a pallet at line 7 that will reduce the walking area space within line 7 that could pose risks to slip/trip fall |  | Serious | Likely | H17 |  | Serious | Likely | H17
| Sleeving Area | Procedure / Process - Lack of | Pallet wrapper is within the area & is causing more congestion |  | Serious | Possible | M13 |  | Serious | Possible | M13
| pallet wrapper if moved | Struck by / Against | when forklift require to grab chep pallets, might create congestion and hit and damage property |  | Serious | Likely | H17 |  | Serious | Likely | H17
| pallet wrapper if moved/dock | process | inbound dock,while receiving if wrapper stops, create a lot of pallet buffer, congesting line 5 , breakdown on HMPS and trouble shooting , colleagues on the way, might hit. |  | Serious | Likely | H17 |  | Serious | Likely | H17

## Pro-Seal
Risk Assessment Worksheet |  | Risk Assessment Worksheet Date: 26-08-2026 Plant / Area: Pro-Seal, |  |  |  | Hierarchy of Control Eliminate Substitute Isolate Engineer Administration PPE |  |  | Sign off | Name | Hierarchy of controls used effectively Justify decision |  |  |  | Risk reduced to ALARP? | Accept / Review RISK? | Signature |  | Review Date
Site Director
Dept Manager
WHS Manager
|  |  |  | RISK IDENTIFICATION |  | Inherent Risk (before controls) |  |  | Controls | Additional Controls | Residual Risk (After Additional Controls) |  |  | Risk Reduction Plan
Ref # | Department / Location | Activity / Process | Hazard Event | Description of event or What If? | Cause (What triggers the risk or hazard? How can it go wrong) | Consequence | Likelihood | Level of Risk | Existing Controls (What is preventing it from occurring?) | Planned mitigating actions (what else will be done?) | Consequence | Likelihood | Level of Risk | Strategic (Y/N) | Last review date | Date for Completion | Responsibility | Owner | Status
1 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Cutting | Operator touching the sharp blade in the tool while pushing/pulling the tool. | 1. Operator error. | Insignificant | Possible | L4 | Admin: SOP highlighting the risk. PPE: Operators must wear fabric gloves. | Admin: Include labelling on tool to highlight risk. | Insignificant | Unlikely | L3 | n
2 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Heat | Operator touching the heated surface of the tool while pushing the tool. | 1. Operator error. | Minor | Possible | M9 | Admin: SOP highlighting the risk. PPE: Operators must wear fabric gloves. | Admin: Include labelling on tool to highlight risk. | Minor | Unlikely | L5 | n
3 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Struck by / Against | Operator getting hit by the tool while pushing the tools into the rack. | 1. Operator forgets to push the safety lock forward. | Minor | Possible | M9 | Admin: SOP highlighting the risk and procedure. |  | Minor | Unlikely | L5 | n
4 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Manual handling | Operator getting back injuries due to move the heavy tool to and from the trolley. | 1. Very heavy tool. >100kg | Major | Possible | H17 |  | Admin: SOP to include minimum 2 people to move the tool. | Major | Unlikely | M12 | y |  |  | PF | MH
5 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Manual handling | Operator getting back injuries due to pushing the trolley loaded with heavy tool. | 1. Very heavy tool. >100kg | Major | Possible | H17 |  | Admin: SOP to include minimum 2 people to move the trolley. | Major | Unlikely | M12 | y |  |  | PF | MH
6 | Lasagne High Risk / Proseal | Loading & Unload Tools from the Tool Rack | Ergonomic | Operator getting ergonomic injuries while trying to remove Proseal arms from the rack. | 1. Tight spot. | Major | Likely | E21 |  | Elimination: Reposition the racks in the way that allows approx. half a meter space for access. | Insignificant | Rare | L1 | n
1 | Lasagne High Risk / Proseal | Setting up Tool in Proseal | Struck by / Against | Personnel struck by moving gate. | 1. Someone else swinged the door. | Minor | Possible | M9 |  | Admin: SOP to include practice caution when opening the gate. | Minor | Rare | L2 | y |  |  | PF | MH
2 | Lasagne High Risk / Proseal | Removing Jammed Trays | Crushing | Operators getting their hands crushed in Proseal. | 1. Operator error. | Serious | Possible | M13 | Isolation: A guard in place to protect accidental access of hands. |  | Serious | Rare | L4 | n
3 | Lasagne High Risk / Proseal | Loading of Films | Manual handling | Operator getting hurt while lifting the films above shoulder level. | 1. Heavy film roll. >15kg | Minor | Possible | M9 | Admin: SOP to include minimum 2 people to lift the film. |  | Minor | Unlikely | L5 | n
4 | Lasagne High Risk / Proseal | Cleaning Dirty Tool in Proseal while Operation. | Heat | Operator touching the heated surface of the tool while attempting to clean the heating surface contaminated with sauces. | 1. Operator error. | Serious | Possible | M13 | Admin: SOP highlighting the risk. PPE: Operators must wear fabric gloves. | Admin: Include labelling on tool to highlight risk. | Serious | Unlikely | M8 | n
5 | Lasagne High Risk / Proseal | Removing waste film from the Proseal. | Ergonomic | Operator getting ergonomic injuries while trying to remove waste film where a valve is in a way. | 1. Valve in a way. | Minor | Likely | M14 |  | Elimination: Relocate the valve so it is not in the way. | Insignificant | Rare | L1
6 | Lasagne High Risk / Proseal | Performing Metal Test on Products | Struck by / Against | Operator getting struck by protruding rods which is part of the rail. | 1. Equipment design. | Minor | Likely | M14 |  | Isolation: Consider a guard or shorten the rod to prevent striking. | Minor | Rare | L2 | y |  |  | eddy | MH
1 | Lasagne High Risk / Proseal | Cleaning the Tools | Crushing | Operator getting finger crushed while assembling the bottom tool after cleaning. | 1. Heavy tool assembly. >15kg | Minor | Possible | M9 | Admin: SOP highlighting the risk and procedure. | Admin: SOP to include minimum 2 people to move the trolley. | Minor | Unlikely | L5 | y
2 | Lasagne High Risk / Proseal | Cleaning the Tools | Manual handling | Operator getting hurt while lifting the bottom tool assembly. | 1. Heavy tool assembly. >15kg | Minor | Possible | M9 | Admin: SOP highlighting the risk and procedure. | Admin: SOP to include minimum 2 people to move the trolley. | Minor | Unlikely | L5 | y |  |  | PF | MH
1 | Lasagne High Risk / X-Ray Checkweighter | Removing Jammed Trays | Friction | Operators getting their hands frictioned by moving conveyor. | 1. Operator error. | Serious | Possible | M13 | Engineering: Safety interlock mechanism in place. |  | Insignificant | Rare | L1 | n
2 | Lasagne High Risk / X-Ray Checkweighter | Removing Jammed Trays | Radiation | Operators exposed to radiation while putting their hands into the X-Ray. | 1. Operator error. | Major | Possible | H17 | Engineering: Safety interlock mechanism in place. |  | Insignificant | Rare | L1 | n
2 | Lasagne High Risk / X-Ray Checkweighter | Removing Jammed Trays | Cutting | Operators getting their hands cut by sharp edges of the lid while shutting it. | 1. Operator error. | Insignificant | Possible | L6 | Admin: Crush point label on lid to highlight risk. | Isolation: Install a rubber seal to isolate the sharp edges. | Insignificant | Rare | L1 | n

## Manual Spinner
Risk Assessment Form
Before
Date of Assessment |  | 29th July
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Manual Spinner
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager
Ranjan |  | Operations Manager
Szymon |  | Engineer
Sean |  | Engineer
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | High Care | Manual handling | Lifting product in to the manual spinner could be above shoulder height causing manual strain to the body |  | Minor | Unlikely | L5 | Manual handling training Light weight leaf veggies | Minor | Unlikely | L5
2 | High Care | Manual handling | Manualy spinning the handle could cause strain to the shoulder |  | Minor | Unlikely | L5 | Manual handling training | Minor | Unlikely | L5
3 | High Care | Struck by / Against | When cranking the handle, if the colleague has let go, the handle may hit the colleague in the hand/arm |  | Minor | Unlikely | L5 |  | Minor | Unlikely | L5
4 | High Care
5 | High Care
6 | High Care
7 | High Care
8 | High Care
9 | High Care

## SML Tumbler
Risk Assessment Form
Before
Date of Assessment |  | Friday 12th June
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Dryer
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager
Ranjan |  | Operations Manager
Szymon |  | Engineer
Sean |  | Engineer
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | High Care | Electrical | Wire could be damaged & expose live wire |  | Minor | Possible | M8 | No control | Minor | Possible | M8 | Safety start up sheet to be drafted for the operator to check the machine daily before start up | Mel | Closed
2 | High Care | Electrical | No isolator on the machine |  | Serious | Possible | M13 | Main isolator on power cable | Minor | Unlikely | L5 | Install a lockable local isolator adjacent to the machine to allow safe isolation during maintenance, cleaning, and emergency situations. | Szymon
3 | High Care | Manual handling | All product is loaded manually lifting from the ground to above should height |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Manual handling training | Szymon Jen | Closed
4 | High Care | Manual handling | All product is unloaded manually, to ground level |  | Serious | Possible | M13 |  | Serious | Possible | M13 | Manual handling training | Szymon Jen | Closed
5 | High Care | Manual handling | Manually push the barrel to unload the product, hard to move |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Make the barrel, easy to move | Szymon
6 | High Care | Entanglement | The lid to the tumbler can be lifted while the machine is still operating and metal paddle still in rotation |  | Extreme | Possible | E22 | E-Stop | Minor | Rare | L3 | Safety switch has been installed, the machine does not run without the guard on | Szymon | Closed
7 | High Care | Crushing | Opening/ closing lid if the operator lets go of the lid it can fall hitting hand |  | Major | Possible | H18 | No control | Minor | Unlikely | L5 | The lid has be taken off the hinge, it is now a mobile lid that has to be placed on the wall | Szymon | Closed

## Risk Assessment Form Washer
Risk Assessment Form
Before
Date of Assessment |  | Friday 12th June
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Washer
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager | Operations
Ranjan |  | Operations Manager | Operations
Szymon |  | Engineer | Projects
Sean |  | Engineer | Maintenance
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | Low Risk | Electrical | No isolator on the machine |  | Serious | Possible | M13 | Power socket next to machine to turn the machine on/off | Serious | Possible | M13 | Install a lockable local isolator adjacent to the machine to allow safe isolation during maintenance, cleaning, and emergency situations. | Szymon | closed
2 | Low Risk | Electrical | Electrical box no lock on the box and the operator can access the electricals |  | Major | Possible | H18 | Side latch installed on the box | Minor | Unlikely | L5 | Fit a lockable electrical enclosure and restrict access to authorised maintenance personnel only. Display appropriate electrical hazard signage. | Szymon | closed
3 | Low Risk | Electrical | Estop is fitted to the control panel of the machine and is away from where the operator is loading product into the machine. |  | Serious | Possible | M13 | Estop on the control panel | Serious | Possible | M13 | Install a additional estop at the front of the machine where the operator is working. Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed
4 | Low Risk | Electrical | Electrical box not IP rated, water can get into the electrical box cause electrical damage |  | Major | Possible | H18 | No control | Major | Possible | H18 | Upgrade the electrical enclosure to an appropriate IP rating (minimum IP56, preferably IP66 if subject to washdowns or heavy splashing). Ensure all cable entries use IP-rated glands. Install a residual current device (RCD) or earth leakage circuit breaker upstream to instantly cut power if a fault occurs. | Szymon | closed
5 | Low Risk | Food spoilage | Plumbing tape was observed hanging above the product and water line, presenting a potential contamination hazard and increasing the risk of product spoilage. |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Remove the plumbing tape immediately and replace it with a permanent food-grade repair. Inspect surrounding pipework and implement routine inspections to prevent contamination risks. | Szymon | closed
6 | Low Risk | Sharp Edge/Impliment | Sharp edges on the machine may cause cuts or lacerations to personnel during operations use, cleaning, or maintenance. |  | Minor | Possible | M8 | No control | Minor | Possible | M8 | De-burr, grind, and smooth all sharp edges. Install edge protection or guards where required and verify all contact surfaces are safe during operation, cleaning, and maintenance. | Szymon | closed
7 | Low Risk | Chemical | Peracetic Acid (PAA) is a corrosive acid used for dosing. Exposure during handling or dosing may cause chemical burns, eye injuries, and respiratory irritation. |  | Major | Likely | E21 | Eye wash station near by PPE, Face shield, Long chemical gloves, Long Apron | Serious | Unlikely | M9 | Short term Place SDS sheets Shadow board required for PPE Chemical bund required to lock chemical Long term Automatic dosing required to reduce manual dosing | Mel HCC Szymon
8 | Low Risk | Entanglement | Operator may place their hands near the exposed chain, creating a risk of entanglement, pinch-point injuries, crushing, or amputation during machine operation. |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Install a fixed guard over the exposed chain to prevent access to moving parts during operation. Ensure guarding complies with relevant machinery safety requirements and is maintained in good condition. Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed
9 | Low Risk | Food spoilage | The gearbox is positioned above the open product and water area. Rust, lubricant, debris, or other contaminants from the gearbox could fall into the product stream, resulting in contamination and potential product spoilage. |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Install a fully enclosed protective housing around the gearbox to prevent rust, lubricant, and debris from entering the product or water stream. Ensure the enclosure is suitable for the operating environment and allows for safe inspection and maintenance. | Szymon
10 | High Care | Crushing | Off loading the product from the washer, the conveyor belt chains and conveyor guards are exposed and potential for the operator to be injured |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Install guarding over the the exposed chain and coveyor guards. Install an E-Stop on high care side Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed

## Tumbler
Risk Assessment Form
Before
Date of Assessment |  | Friday 12th June
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Tumbler
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager | Operations
Ranjan |  | Operations Manager | Operations
Szymon |  | Engineer | Projects
Sean |  | Engineer | Maintenance
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | High Care | Electrical | Wire could be tangled with the tumbler as the tumbler moves |  | Minor | Unlikely | L5 | Wire on the ground | Minor | Unlikely | L5 | Hard wire the cabel to the wall shorten the lead | Szymon | closed
2 | High Care | Structural damage | Machine in operation moves and tilts could cause damage to the walls |  | Minor | Unlikely | L5 | No control | Minor | Unlikely | L5 | Moved away from the wall - | Szymon | closed
3 | High Care | Fall from height | Dolly lifters do not have a safety latch on the lifter to secure inplace while it is lifted during cycle |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Install safety latch on the rail Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed
4 | High Care | Manual handling | Removing product from the tumbler, operator needs to lean and remove the product by hand |  | Major | Possible | H18 | No control | Major | Possible | H18 | Implement operator to use a shovel to remove the product into dolly. Need to confirm how the operator will access inside of the machine while 2 dollies are in front of the machine. Updated as per the SOP for unloading product - cmpleted | Jen | closed
5 | High Care | Manual handling | Changing of the scrapper will be done in an awakward position, will cause a sore back |  | Major | Possible | H18 | No control | Major | Possible | H18 | Review the position the paddle needs to be in for the change- recommend the paddle go to the bottom of the bowl to remove Manual handling only for changing of the paddle, can not engineer this out | Jen | closed
6 | High Care | Struck by / Against | When the lid of the tumbler is open, colleagues could hit their head |  | Minor | Possible | M8 | No control | Minor | Possible | M8 | Need to add in the SOP awarness | Jen | closed
7 | High Care | Struck by / Against | When the tumbler is in motion, going down with the tumbler could strike an operator |  | Minor | Possible | M8 | Control panel is located on the front screen | Minor | Possible | M8 | Guarding or rails near the lifter to stop pedestrians from walking in the line of fire Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed
8 | High Care | Trip | Dolly lifter legs could cause a trip hazard |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Guarding around the legs or paint on the ground Accepting the risk, signed off by Andy. M & Aaron. B | Szymon | closed

## Risk Assessment Form Slicer
Risk Assessment Form
Before
Date of Assessment |  | Friday 12th June
Department |  | High Care | [5 empty] | Risk Matrix
Process / Machine |  | Slicer
Site Location |  | TK
Risk Assessment Team
Name |  | Title | Work Area
Jennifer Galea |  | Operations Manager
Ranjan |  | Operations Manager
Szymon |  | Engineer
Sean |  | Engineer
Caroyln |  | WHS | Contractor Safety
Mel |  | WHS | WHS
Risk Identification |  |  |  |  | Inherent Risk (Before controls) |  |  | Controls | Residual Risk (After Controls) |  |  | Additional Required Controls | Action By | Close Out | Pictures | Pictures
No | Location | Hazard Event | Hazard | Impact (So What? What are the impacts if it occurs) | Consequence | Likelihood | Level of Risk | Existing Controls | Consequence2 | Likelihood2 | Level of Risk. | Planned mitigating actions (what else will be done?) | Who | Open / Closed
1 | High Care | Electrical | Wire could be damaged due to a mobile machine causing exposed wire & electrocution |  | Serious | Possible | M13 | No control | Serious | Unlikely | M9 | Safety start up sheet to be drafted for the operator to check the machine daily before start up. Hard wire the machine to eleminated wires from being damaged | Mel Szymon | closed
2 | High Care | Electrical | No isolator on the machine, maintenance technician performs maintenance checks for breakdowns |  | Serious | Possible | M13 | LOTO Process | Minor | Unlikely | L5 | Install a local, lockable rotary isolation switch directly on the unit frame to ensure positive mechanical isolation. | Szymon | closed
3 | High Care | Electrical | Water or cleaning solution sprays directly onto or seeps into the control box during daily cleaning or contract cleaning |  | Serious | Possible | M13 | No control | Serious | Possible | M13 | Upgrade or replace the control box to achieve an IP66 & adding rubber around egdes to reduce water getting in. Add a fan to cool the control panel | Szymon | closed
4 | High Care | Amputation | Operator places their hand into the feeding hole to clear a jam or push vegetables further down while the machine is running. |  | Extreme | Likely | E24 | No control | Serious | Unlikely | M9 | Extend the feed chute length to enforce "Safe by Distance" reach barriers (AS/NZS 4024.1801). Key lock has been installed on this machine that operates the feeding holes. When the key is de-activated the power will not run to this side of the machine. only the operation manager has access to this feeding hole | Szymon | closed
5 | High Care | Entanglement | Loose clothing, long hair, or jewellery drops into the feeding hole. |  | Major | Likely | E21 | No control | Minor | Unlikely | L5 | Install a restricted-throat baffle plate or an angled funnel over the feeding opening to block drop-in access. | Szymon | closed
6 | High Care | Amputation | Operator attempts to clear debris and hand is pulled into the machine cutting finger / hand. |  | Extreme | Likely | E24 | Signage on the machine, don’t place hand into machine | Minor | Unlikely | L5 | Install fixed perimeter guards length to enforce "Safe by Distance" reach barriers (AS/NZS 4024.1801). Guarding has been installed with an interlock, when the door is opened the machine will disengage stopping the blade, The blade has an addiotnal magnent interlocking Operators can not reach within the machine with the guarding on | Szymon | closed
7 | High Care | Amputation | Operator reaches their hand directly up into either of the bottom discharge holes to pull out packed or clogged vegetable debris while the machine is running or coasting. |  | Extreme | Likely | E24 | No control | Minor | Unlikely | L5 | Fabricate extended discharge tunnels or specialized discharge chutes that physically exceed the arm-reach safety distances required by AS/NZS 4024.1801. Guarding has been installed with an interlock, when the door is opened the machine will disengage stopping the blade, The blade has an addiotnal magnent interlocking Operators can not reach within the machine with the guarding on | Szymon | closed
8 | High Care | Amputation | Operator reaches over the low side-guard vegetable conveyor belt to adjust a vegetable or clean the belt while it is in motion, getting drawn into the cutting head. |  | Extreme | Likely | E24 | No control | Minor | Unlikely | L5 | Fabricate extended conveyors that physically exceed the arm-reach safety distances required by AS/NZS 4024.1801. Guarding has been installed with an interlock, when the door is opened the machine will disengage stopping the blade, The blade has an addiotnal magnent interlocking Operators can not reach within the machine with the guarding on | Szymon | closed
9 | High Care | Entanglement | Operator opens the main silver casing (where the hinges and black knobs are) to clean the blades or change the cutting disc while the motor is spinning or coasting. |  | Extreme | Likely | E24 | No control | Minor | Unlikely | L5 | Install safety interlock on the door, when the machine is stopped or guard is opened the blade immeditely stops Guarding has been installed with an interlock, when the door is opened the machine will disengage stopping the blade, The blade has an addiotnal magnent interlocking Operators can not reach within the machine with the guarding on | Szymon | closed
10 | High Care | Laceration | A worker attempts to change the blades or clean inside the cutting chamber, could cause laceration. |  | Major | Possible | H18 | PPE available | Major | Possible | H18 | Shadow board on where to store blades are on the machine, use of specialized, heavy-duty cut-resistant PPE gloves during blade changeouts. SOP | Jen | closed
11 | High Care | Laceration | Because there is no active braking system, the heavy blade disc continues to spin silently operator could open the guarding & blade could still be spinning causing amputation |  | Extreme | Likely | E24 | No control | Minor | Unlikely | L5 | Fit a Solenoid Guard Locking Switch (Power-to-Unlock) paired with a Zero-Speed Monitor or time-delay safety relay. The chamber will physically remain locked shut until the blades hit or put the break system on the motor to stop the blades from spinning Guarding has been installed with an interlock, when the door is opened the machine will disengage stopping the blade, The blade has an addiotnal magnent interlocking Operators can not reach within the machine with the guarding on | Szymon | closed
12 | High Care | Ergonomic | Operators are forced to work in a sustained forward-flexed (hunched) position to load or unload the machine for hours at a time. |  | Major | Possible | H18 | Manual handling training | Major | Possible | H18 | Mount and anchor the entire machine chassis onto a robust engineered steel sub-base (plinth) to lift the operational height to waist/chest level (900 to 1200mm) as per the standard Accpeting the risk | Szymon | closed
13 | High Care | Manual handling | Feeding the machine is at a lower level & an operator will be in a hunched position could cause muscel starin |  | Major | Possible | H18 | Manual handling training | Major | Possible | H18 | Place the crates on wheels so they are not sitting on the floor | Jen | closed
14 | High Care | Manual handling | Picking up sliced product from ground level at the exit of the machine could cause muscle starain |  | Major | Possible | H18 | Manual handling training | Major | Possible | H18 | Place the crates on wheels so they are not sitting on the floor | Jen | closed

## Actions List (hidden)
Machine | Hazard | Action | Responsible | Status | Due Date | Comments
Dryer | 415 volts 3 phase,does not have a reset button, | Install a magnetic contactor or a No-Volt Release (NVR) switch. This ensures that if power is lost or an E-stop is pressed, the machine cannot automatically restart when power is restored until a manual reset button is pressed.
Dryer | Not IP rated, Water will get in to the eletrical box of the machine & could cause electrical damage | Upgrade the electrical enclosure to an appropriate IP rating (minimum IP56, preferably IP66 if subject to washdowns or heavy splashing). Ensure all cable entries use IP-rated glands. Install a residual current device (RCD) or earth leakage circuit breaker upstream to instantly cut power if a fault occurs.
Dryer | Isolator switch is made from cheap plastic could break easily | Replace the plastic switch with a heavy-duty, industrial-grade metal or impact-resistant polycarbonate isolator switch rated for the machine's load
Dryer | All buttons on the machine are not water proof & could cause water damage to the machine or casue electric shock | Retrofit the control panel with IP65/IP67 rated waterproof pushbuttons or install a heavy-duty flexible silicone/rubber waterproof boot over the existing buttons.
Dryer | Gas struts on the lifter does not soft close & could cause fractured fingers if operators do not keep fingers clear | Replace existing struts with damped/soft-close gas struts or mechanical speed-restricting dampers. Install mechanical safety catch pins or a secondary locking latch to hold the lid securely open during loading/unloading.
Dryer | No break on machine, when door is lifted the basket within still spins rapidly | Link this to the safety interlock (see below) so the door physically cannot be unlocked or opened until the basket has stopped spinning entirely (timed delay lock).
Dryer | No interlock safety swicth on the lid | Install a Category 4/PLe rated dual-channel safety interlock Wire the interlock directly into a safety relay so that opening the lid immediately cuts power to the motor driving the basket.
Dryer | Could hit head on the lid of the dryer | De-burr, grind down, and radius all sharp sheet metal edges.
Washer | No isolator on the machine | Install a lockable local isolator adjacent to the machine to allow safe isolation during maintenance, cleaning, and emergency situations. Incorporate the isolator into the site's Lockout/Tagout (LOTO) procedure.
Washer | Electrical box needs to be locked with a maintenance guard key | Fit a lockable electrical enclosure and restrict access to authorised maintenance personnel only. Implement key control procedures and display appropriate electrical hazard signage.
Washer | Only one E-stop is fitted to the machine, which is inadequate for its size. | Additional E-stops should be installed to ensure safe access to emergency shutdown controls for personnel working around the machine, particularly during decanting operations.
Washer | Not IP rated, Water will get in to the eletrical box of the machine & could cause electrical damage | Upgrade the electrical enclosure to an appropriate IP rating (minimum IP56, preferably IP66 if subject to washdowns or heavy splashing). Ensure all cable entries use IP-rated glands. Install a residual current device (RCD) or earth leakage circuit breaker upstream to instantly cut power if a fault occurs.
Washer | Plumbing tape was observed hanging above the product and water line, presenting a potential contamination hazard and increasing the risk of product spoilage. | Remove the plumbing tape immediately and replace it with a permanent food-grade repair. Inspect surrounding pipework and implement routine inspections to prevent contamination risks.
Washer | Sharp Edge Hazard: Sharp edges on the machine may cause cuts or lacerations to personnel during operations use, cleaning, or maintenance. | De-burr, grind, and smooth all sharp edges. Install edge protection or guards where required and verify all contact surfaces are safe during operation, cleaning, and maintenance.
Washer | Chemical Exposure Hazard: Peracetic Acid (PAA) is a corrosive acid used for dosing. Exposure during handling or dosing may cause chemical burns, eye injuries, and respiratory irritation. | Place SDS sheets near by, Shadow board required for PPE Chemical bund required to lock chemical Automatic dosing required to reduce manual dosing
Washer | personnel may place their hands near the exposed chain, creating a risk of entanglement, pinch-point injuries, crushing, or amputation during machine operation. | Install a fixed guard over the exposed chain to prevent access to moving parts during operation. Ensure guarding complies with relevant machinery safety requirements and is maintained in good condition.
Washer | The gearbox is positioned above the open product and water area. Rust, lubricant, debris, or other contaminants from the gearbox could fall into the product stream, resulting in contamination and potential product spoilage. | Install a fully enclosed protective housing around the gearbox to prevent rust, lubricant, and debris from entering the product or water stream. Ensure the enclosure is suitable for the operating environment and allows for safe inspection and maintenance.
Slicer | wire could be damaged due to a mobile machine causing exposed wire & electrocution | Safety start up form Have the wire coming from the top & not long enough to touch the ground ?
Slicer | No isolator on the machine, A maintenance technician performs maintenance checks for breakdowns | Install a local, lockable rotary isolation switch directly on the unit frame to ensure positive mechanical isolation.
Slicer | Water or cleaning solution sprays directly onto or seeps into the control box during daily cleaning or contract cleaning | Upgrade or replace the control box to achieve an IP66 & adding rubber around egdes to reduce water getting in. Add a fan to cool the control panel
Slicer | An operator reaches their hand inside the chute to clear a jam or push vegetables further down while the machine is running. | Extend the feed chute length to enforce "Safe by Distance" reach barriers (AS/NZS 4024.1801).
Slicer | Loose clothing, long hair, or jewellery drops into the feeding hole. | Install a restricted-throat baffle plate or an angled funnel over the feeding opening to block drop-in access.
Slicer | An operator attempts to clear debris near the rollers or the cutting head interface. Hand or fingers get caught between the moving belt and the frame. | Install fixed perimeter guards length to enforce "Safe by Distance" reach barriers (AS/NZS 4024.1801).
Slicer | An operator reaches their hand directly up into either of the bottom discharge holes to pull out packed or clogged vegetable debris while the machine is running or coasting. | Fabricate extended discharge tunnels or specialized discharge chutes that physically exceed the arm-reach safety distances required by AS/NZS 4024.1801.
Slicer | Operator reaches over the low side-guard to adjust a vegetable or clean the belt while it is in motion, getting drawn into the cutting head. | Fabricate extended conveyors that physically exceed the arm-reach safety distances required by AS/NZS 4024.1801.
Slicer | Operator opens the main silver casing (where the hinges and black knobs are) to clean the blades or change the cutting disc while the motor is spinning or coasting. | Install safety break on the motor for when the machine is stopped or guard is opened the blade immeditely stops
Slicer | A worker attempts to change the blades or clean inside the cutting chamber, could cause laceration. | Shadow board on where to store blades, Mandate the use of specialized, heavy-duty cut-resistant PPE gloves during blade changeouts. SOP
Slicer | Because there is no active braking system, the heavy blade disc continues to spin silently under its own inertia An operator could open the guarding & blade could still be spinning causing amputation | Fit a Solenoid Guard Locking Switch (Power-to-Unlock) paired with a Zero-Speed Monitor or time-delay safety relay. The chamber will physically remain locked shut until the blades hit or put the break system on the motor to stop the blades from spinning
Slicer | Operators are forced to work in a sustained forward-flexed (hunched) position to load or unload the machine for hours at a time. | Mount and anchor the entire machine chassis onto a robust engineered steel sub-base (plinth) to lift the operational height to waist/chest level (900 to 1200mm) as per the standard
Slicer | Feeding the machine is at a lower level & an operator will be in a hunched position could cause muscel starin | place the crates on wheels so they are not sitting on the floor
Slicer | picking up sliced product from ground level at the exit of the machine could cause muscel starin | place the crates on wheels so they are not sitting on the floor

## Requirements (hidden)
Shadow board
Chemical bund
Chemical trolley
Table
x6 scales
Knife sharpner

## Brainstorming (hidden)
Brainstorming Record - examples

## RA Tool Kit DO NOT DELETE (hidden)
RISK MATRIX
Hierarchy of Control |  |  |  |  | LIKELIHOOD
Elimination |  | Do we still have to do this? |  |  | A | Almost certain to happen |  |  |  | FREQUENCY | Multiple/ 12 months
Substitution |  | Is there another way or product? |  |  | B | Likely to happen at some point |  |  |  |  | Once/ 12 months
Redesign/Engineer |  | Can the equipment or process be modified? |  |  | C | Moderate, possible; heard of so it might happen |  |  |  |  | Once / 12 months to 5 years
Isolation/Guarding |  | Will guarding or some type of barrier help? |  |  | D | Unlikely, not likely to happen |  |  |  |  | Once/ 5 to 10 years
Administration |  | Will a written procedure and/or training help? |  |  | E | Rare, practically impossible |  |  |  |  | Once / >10 years
PPE |  | Is personal protective equipment adequate?
MAXIMUM REASONABLE CONSEQUENCE
Consequence |  | Injury (I) |  |  |  | Environmental (E) |  |  |  |  | Plant/equipment
5 EXTREME |  | Critical Incident |  |  |  | Regional environmental impact/ecosystem damage. Impact causing mine or business closure. E.g. Major release off site with long term detrimental effect |  |  |  |  | Machine Unrepairable
A fatality, permanent disability. E.g. loss of limb, body part, burs to 30% of body
4 MAJOR |  | Loss Time Injury |  |  |  | Substantial environmental damage which could result in major financial loss and/or prosecution. E.g. Off-site release resulting in local ecosystem damage |  |  |  |  | 6 - 20 Days machine downtime
Work injury that results in the worker being unable to return to work the next working day, determined as unfit on a Workcover medical certificate
3 SERIOUS |  | Medical Treatment Injury & Restricted Work Injury |  |  |  | Substantial temporary or minor long-term damage, release immediately contained with outside assistance e.g. A minor water discharge or large hydrocarbon spill. Legal non-compliance. |  |  |  |  | 2-5 Days machine downtime
Work injury that results in the worker requiring a return-to-work suitable duties plan. Worker works reduced hours
2 MINOR |  | Medical Treatment Injury |  |  |  | Temporary or minor damage, non-compliance with internal environmental target, no legal breach, e.g. Minor spill |  |  |  |  | 1 day machine downtime
any injury requiring further treatment from a medical practitioner or any administration of a drug. Worker returns to work immediately
1 INSIGNIFICANT |  | First Aid Injury |  |  |  | No detrimental effect, low financial loss, negligible environmental impact |  |  |  |  | No Machine downtime
Any injuries requiring first aid treatment only
RISK SCORE MATRIX
LEVEL OF CORRECTIVE ACTION |  |  |  | LIKELIHOOD | [7 empty] | Least Effective Most Effective
Risk Score | Risk |  | What should I do? | CONSEQUENCE |  |  | A- Certain | B - Likely | C - Moderate | D - Unlikely | E - Rare
E20 - 25 | Extreme |  | Immediate action required; further reduction needed. If not possible, Chief Operating Officer approval required |  | 1 – Extreme |  | E25 | E24 | E22 | H19 | H15
H15 – 19 | Major |  | Head of Manufacturing and senior management Approval |  | 2 – Major |  | E23 | E21 | H18 | M14 | M10
M7 - 14 | Serious |  | Management responsibility must be specified |  | 3 – Serious |  | E20 | H17 | M13 | M9 | L6
L4 – 6 | Minor |  | Manage through outlined procedures |  | 4 – Minor |  | H16 | M12 | M8 | L5 | L3
L1 – 3 | Insignificant |  | Manage through outlined procedures |  | 5 - Insignificant |  | M11 | M7 | L4 | L2 | L1

## Consequences (hidden)
Return to Front Screen

## Likelihood (hidden)
LIKELIHOOD
Likelihood | (2) Description | (1) Frequency | Return to Front Screen
A Almost Certain | The event is expected to occur in most circumstances | Multiple / 12 months
B Likely | The event will probably occur in most circumstances | Once / 12 months
C Possible | The event may occur at some time | Once / 12 months – 5 years
D Unlikely | The event has not occurred in our company, but has occurred within the industry as a whole on a number of occasions | Once / 5 – 10 years
E Rare | Event has not been known to occur in our company, but has been known to occur infrequently within the industry and is only likely to occur in exceptional circumstances. | Once / > 10 years
- If a time frame can be determined, use definition (1)
- If the timeframe cannot be determined, use definition (2) by assessing the inherent likelihood of the risk occurring given all available information.

## Risk Monitoring tracking (hidden)
RISK MONITORING STATUS
TERM | DEFINITION | Return to Front Screen
New | Use this status for newly entered risk items requiring attention.
Action | The Management Team have planned or require further action in order to accept the risk.
Monitor and Review | Where all practical and reasonable mitigation efforts have been made, The Management Team expect ongoing monitoring and review to ensure controls continue to act as intended and to seek opportunities for further improvement to controls whereever possible. NOTE refer to Safety Risk Management for additional expectations on regular safety interactions.
Mitigated | NO LONGER USED. The risk is one of other options
Transferred | The risk is outside the control of the Group. On going monitoring is required to ensure that the risk has been mitigated to an acceptable level.
Active | NO LONGER USED. The risk is one of other options
Closed | The threat of the risk event occurring has passed.

## Matrix (hidden)
C L | ALMOST CERTAIN | LIKELY | POSSIBLE | UNLIKELY | RARE | Likelihood | Description | Frequency
Extreme | E25 | E24 | E22 | H19 | H15 | A Almost Certain | The event is expected to occur in most circumstances | Multiple / 12 months
Major | E23 | E21 | H18 | M14 | M10 | B Likely | The event will probably occur in most circumstances | Once / 12 months
Serious | E20 | H17 | M13 | M9 | L6 | C Possible | The event may occur at some time | Once / 12 months – 5 years
Minor | H16 | M12 | M8 | L5 | L3 | D Unlikely | The event has not occurred in our company, but has occurred within the industry as a whole on a number of occasions | Once / 5 – 10 years
Insignificant | M11 | M7 | L4 | L2 | L1 | E Rare | Event has not been known to occur in our company, but has been known to occur infrequently within the industry. | Once / > 10 years
Risk Rating |  | Level of Corrective Action Required |  |  |  | Risk Rating |  | Consequence
Extreme | E20 - 25 | Immediate action required, further reduction needed. If not possible, Site Director approval required |  |  |  | Extreme | E20 - 25 | Fatality / Perminant disability
Major | H16 - 19 | Senior management attention needed |  |  |  | Major | H15 - 19 | Injury /Illness that results in worker not being able to attend work on the next scheduled day (LTI)
Serious | M7 - 15 | Management responsibility must be specified |  |  |  | Serious | M7 - 14 | Injury/Illness that results in worker returning to work on modified work activity (Diablating Injury)
Minor | L4 - 6 | Manage by outine procedure |  |  |  | Minor | L4 - 6 | Injury/Illness that results in worker returning to work on normal work activity (MTI)
Insignificant | L1 - 3 | Manage by outine procedure |  |  |  | Insignificant | L1 - 3 | Injury requiring First Aid only

## Do not delete (hidden)
Return to Front Screen
[7 empty] | Number of risk items | Strategic | Extreme | High | Moderate | Low | Total
RISK Category | Activity / Process | CONSEQUENCE | LIKELIHOOD | Strategic | Corrective Action Status |  | Safety and Health-Injury / illness(I) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Safety and Health-Injury / illness(I) |  | Extreme | Almost Certain | YES | Open |  | Environment (E) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Environment (E) |  | Major | Likely | NO | Closed |  | Community (C) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Community (C) |  | Serious | Possible |  |  |  | Reputatiion (R) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Reputatiion (R) |  | Minor | Unlikely |  |  |  | Damage / Loss (D) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Damage / Loss (D) |  | Insignificant | Rare | [5 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[8 empty] | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[7 empty] | Total Risks |  |  |  |  | #VALUE!
Impact Options | Status Options | Owner |  |  |  | Safety and Health-Injury/illness (I), Environment (E), Community (C), Reputation (R) or Damage/Loss (D)
1. Safety & Health Acute Injury/Illness/Death 2. Reputational damage 3. Regulator attention 4. Significant financial loss 5. Productivity loss >3 days | Completed | Managing Director
1. Safety & Health Long term Illness/Death 2. Reputational damage 3. Regulator attention 4. Significant financial loss 5. Productivity loss >3 days | 75 - 90% | Operations Manager
1. Safety & Health Injury/Illness 2. Minor productivity loss <1 - 3 days 3. Minor financial loss | 50 - 74% | OHS Manager
1. Environmental damage long term 2. Reputation 3. Regulator attention 4. Significant financial loss 5. Productivity loss >3 days | 35 - 49% | Yard Supervisor
1. Environmental damage short term 2. Reputation 3. Regulator attention 4. Minor/Moderate financial loss 5. Productivity loss <3 days | 20 - 34% | Cement Coordinator
1. Equipment damage 2. Productivity loss 3. Financial loss | 10 - 19% | Other personnel
1. Productivity loss 2. Financial loss | 0 - 9%
1. Reputational loss 2. Productivity loss 3. Financial loss | Not started
Dates
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-11
2019-01-12
2019-01-13
2019-01-14
2019-01-15
2019-01-16
2019-01-17
2019-01-18
2019-01-19
2019-01-20
2019-01-21
2019-01-22
2019-01-23
2019-01-24
2019-01-25
2019-01-26
2019-01-27
2019-01-28
2019-01-29
2019-01-30
2019-01-31
2019-02-01
2019-02-02
2019-02-03
2019-02-04
2019-02-05
2019-02-06
2019-02-07
2019-02-08
2019-02-09
2019-02-10
2019-02-11
2019-02-12
2019-02-13
2019-02-14
2019-02-15
2019-02-16
2019-02-17
2019-02-18
2019-02-19
2019-02-20
2019-02-21
2019-02-22
2019-02-23
2019-02-24
2019-02-25
2019-02-26
2019-02-27
2019-02-28
2019-03-01
2019-03-02
2019-03-03
2019-03-04
2019-03-05
2019-03-06
2019-03-07
2019-03-08
2019-03-09
2019-03-10
2019-03-11
2019-03-12
2019-03-13
2019-03-14
2019-03-15
2019-03-16
2019-03-17
2019-03-18
2019-03-19
2019-03-20
2019-03-21
2019-03-22
2019-03-23
2019-03-24
2019-03-25
2019-03-26
2019-03-27
2019-03-28
2019-03-29
2019-03-30
2019-03-31
2019-04-01
2019-04-02
2019-04-03
2019-04-04
2019-04-05
2019-04-06
2019-04-07
2019-04-08
2019-04-09
2019-04-10
2019-04-11
2019-04-12
2019-04-13
2019-04-14
2019-04-15
2019-04-16
2019-04-17
2019-04-18
2019-04-19
2019-04-20
2019-04-21
2019-04-22
2019-04-23
2019-04-24
2019-04-25
2019-04-26
2019-04-27
2019-04-28
2019-04-29
2019-04-30
2019-05-01
2019-05-02
2019-05-03
2019-05-04
2019-05-05
2019-05-06
2019-05-07
2019-05-08
2019-05-09
2019-05-10
2019-05-11
2019-05-12
2019-05-13
2019-05-14
2019-05-15
2019-05-16
2019-05-17
2019-05-18
2019-05-19
2019-05-20
2019-05-21
2019-05-22
2019-05-23
2019-05-24
2019-05-25
2019-05-26
2019-05-27
2019-05-28
2019-05-29
2019-05-30
2019-05-31
2019-06-01
2019-06-02
2019-06-03
2019-06-04
2019-06-05
2019-06-06
2019-06-07
2019-06-08
2019-06-09
2019-06-10
2019-06-11
2019-06-12
2019-06-13
2019-06-14
2019-06-15
2019-06-16
2019-06-17
2019-06-18
2019-06-19
2019-06-20
2019-06-21
2019-06-22
2019-06-23
2019-06-24
2019-06-25
2019-06-26
2019-06-27
2019-06-28
2019-06-29
2019-06-30
2019-07-01
2019-07-02
2019-07-03
2019-07-04
2019-07-05
2019-07-06
2019-07-07
2019-07-08
2019-07-09
2019-07-10
2019-07-11
2019-07-12
2019-07-13
2019-07-14
2019-07-15
2019-07-16
2019-07-17
2019-07-18
2019-07-19
2019-07-20
2019-07-21
2019-07-22
2019-07-23
2019-07-24
2019-07-25
2019-07-26
2019-07-27
2019-07-28
2019-07-29
2019-07-30
2019-07-31
2019-08-01
2019-08-02
2019-08-03
2019-08-04
2019-08-05
2019-08-06
2019-08-07
2019-08-08
2019-08-09
2019-08-10
2019-08-11
2019-08-12
2019-08-13
2019-08-14
2019-08-15
2019-08-16
2019-08-17
2019-08-18
2019-08-19
2019-08-20
2019-08-21
2019-08-22
2019-08-23
2019-08-24
2019-08-25
2019-08-26
2019-08-27
2019-08-28
2019-08-29
2019-08-30
2019-08-31
2019-09-01
2019-09-02
2019-09-03
2019-09-04
2019-09-05
2019-09-06
2019-09-07
2019-09-08
2019-09-09
2019-09-10
2019-09-11
2019-09-12
2019-09-13
2019-09-14
2019-09-15
2019-09-16
2019-09-17
2019-09-18
2019-09-19
2019-09-20
2019-09-21
2019-09-22
2019-09-23
2019-09-24
2019-09-25
2019-09-26
2019-09-27
2019-09-28
2019-09-29
2019-09-30
2019-10-01
2019-10-02
2019-10-03
2019-10-04
2019-10-05
2019-10-06
2019-10-07
2019-10-08
2019-10-09
2019-10-10
2019-10-11
2019-10-12
2019-10-13
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-19
2019-10-20
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-26
2019-10-27
2019-10-28
2019-10-29
2019-10-30
2019-10-31
2019-11-01
2019-11-02
2019-11-03
2019-11-04
2019-11-05
2019-11-06
2019-11-07
2019-11-08
2019-11-09
2019-11-10
2019-11-11
2019-11-12
2019-11-13
2019-11-14
2019-11-15
2019-11-16
2019-11-17
2019-11-18
2019-11-19
2019-11-20
2019-11-21
2019-11-22
2019-11-23
2019-11-24
2019-11-25
2019-11-26
2019-11-27
2019-11-28
2019-11-29
2019-11-30
2019-12-01
2019-12-02
2019-12-03
2019-12-04
2019-12-05
2019-12-06
2019-12-07
2019-12-08
2019-12-09
2019-12-10
2019-12-11
2019-12-12
2019-12-13
2019-12-14
2019-12-15
2019-12-16
2019-12-17
2019-12-18
2019-12-19
2019-12-20
2019-12-21
2019-12-22
2019-12-23
2019-12-24
2019-12-25
2019-12-26
2019-12-27
2019-12-28
2019-12-29
2019-12-30
2019-12-31
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-11
2020-01-12
2020-01-13
2020-01-14
2020-01-15
2020-01-16
2020-01-17
2020-01-18
2020-01-19
2020-01-20
2020-01-21
2020-01-22
2020-01-23
2020-01-24
2020-01-25
2020-01-26
2020-01-27
2020-01-28
2020-01-29
2020-01-30
2020-01-31
2020-02-01
2020-02-02
2020-02-03
2020-02-04
2020-02-05
2020-02-06
2020-02-07
2020-02-08
2020-02-09
2020-02-10
2020-02-11
2020-02-12
2020-02-13
2020-02-14
2020-02-15
2020-02-16
2020-02-17
2020-02-18
2020-02-19
2020-02-20
2020-02-21
2020-02-22
2020-02-23
2020-02-24
2020-02-25
2020-02-26
2020-02-27
2020-02-28
2020-02-29
2020-03-01
2020-03-02
2020-03-03
2020-03-04
2020-03-05
2020-03-06
2020-03-07
2020-03-08
2020-03-09
2020-03-10
2020-03-11
2020-03-12
2020-03-13
2020-03-14
2020-03-15
2020-03-16
2020-03-17
2020-03-18
2020-03-19
2020-03-20
2020-03-21
2020-03-22
2020-03-23
2020-03-24
2020-03-25
2020-03-26
2020-03-27
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12
2020-04-13
2020-04-14
2020-04-15
2020-04-16
2020-04-17
2020-04-18
2020-04-19
2020-04-20
2020-04-21
2020-04-22
2020-04-23
2020-04-24
2020-04-25
2020-04-26
2020-04-27
2020-04-28
2020-04-29
2020-04-30
2020-05-01
2020-05-02
2020-05-03
2020-05-04
2020-05-05
2020-05-06
2020-05-07
2020-05-08
2020-05-09
2020-05-10
2020-05-11
2020-05-12
2020-05-13
2020-05-14
2020-05-15
2020-05-16
2020-05-17
2020-05-18
2020-05-19
2020-05-20
2020-05-21
2020-05-22
2020-05-23
2020-05-24
2020-05-25
2020-05-26
2020-05-27
2020-05-28
2020-05-29
2020-05-30
2020-05-31
2020-06-01
2020-06-02
2020-06-03
2020-06-04
2020-06-05
2020-06-06
2020-06-07
2020-06-08
2020-06-09
2020-06-10
2020-06-11
2020-06-12
2020-06-13
2020-06-14
2020-06-15
2020-06-16
2020-06-17
2020-06-18
2020-06-19
2020-06-20
2020-06-21
2020-06-22
2020-06-23
2020-06-24
2020-06-25
2020-06-26
2020-06-27
2020-06-28
2020-06-29
2020-06-30
2020-07-01
2020-07-02
2020-07-03
2020-07-04
2020-07-05
2020-07-06
2020-07-07
2020-07-08
2020-07-09
2020-07-10
2020-07-11
2020-07-12
2020-07-13
2020-07-14
2020-07-15
2020-07-16
2020-07-17
2020-07-18
2020-07-19
2020-07-20
2020-07-21
2020-07-22
2020-07-23
2020-07-24
2020-07-25
2020-07-26
2020-07-27
2020-07-28
2020-07-29
2020-07-30
2020-07-31
2020-08-01
2020-08-02
2020-08-03
2020-08-04
2020-08-05
2020-08-06
2020-08-07
2020-08-08
2020-08-09
2020-08-10
2020-08-11
2020-08-12
2020-08-13
2020-08-14
2020-08-15
2020-08-16
2020-08-17
2020-08-18
2020-08-19
2020-08-20
2020-08-21
2020-08-22
2020-08-23
2020-08-24
2020-08-25
2020-08-26
2020-08-27
2020-08-28
2020-08-29
2020-08-30
2020-08-31
2020-09-01
2020-09-02
2020-09-03
2020-09-04
2020-09-05
2020-09-06
2020-09-07
2020-09-08
2020-09-09
2020-09-10
2020-09-11
2020-09-12
2020-09-13
2020-09-14
2020-09-15
2020-09-16
2020-09-17
2020-09-18
2020-09-19
2020-09-20
2020-09-21
2020-09-22
2020-09-23
2020-09-24
2020-09-25
2020-09-26
2020-09-27
2020-09-28
2020-09-29
2020-09-30
2020-10-01
2020-10-02
2020-10-03
2020-10-04
2020-10-05
2020-10-06
2020-10-07
2020-10-08
2020-10-09
2020-10-10
2020-10-11
2020-10-12
2020-10-13
2020-10-14
2020-10-15
2020-10-16
2020-10-17
2020-10-18
2020-10-19
2020-10-20
2020-10-21
2020-10-22
2020-10-23
2020-10-24
2020-10-25
2020-10-26
2020-10-27
2020-10-28
2020-10-29
2020-10-30
2020-10-31
2020-11-01
2020-11-02
2020-11-03
2020-11-04
2020-11-05
2020-11-06
2020-11-07
2020-11-08
2020-11-09
2020-11-10
2020-11-11
2020-11-12
2020-11-13
2020-11-14
2020-11-15
2020-11-16
2020-11-17
2020-11-18
2020-11-19
2020-11-20
2020-11-21
2020-11-22
2020-11-23
2020-11-24
2020-11-25
2020-11-26
2020-11-27
2020-11-28
2020-11-29
2020-11-30
2020-12-01
2020-12-02
2020-12-03
2020-12-04
2020-12-05
2020-12-06
2020-12-07
2020-12-08
2020-12-09
2020-12-10
2020-12-11
2020-12-12
2020-12-13
2020-12-14
2020-12-15
2020-12-16
2020-12-17
2020-12-18
2020-12-19
2020-12-20
2020-12-21
2020-12-22
2020-12-23
2020-12-24
2020-12-25
2020-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2020-12-31
2021-01-01
2021-01-02
2021-01-03
2021-01-04
2021-01-05
2021-01-06
2021-01-07
2021-01-08
2021-01-09
2021-01-10
2021-01-11
2021-01-12
2021-01-13
2021-01-14
2021-01-15
2021-01-16
2021-01-17
2021-01-18
2021-01-19
2021-01-20
2021-01-21
2021-01-22
2021-01-23
2021-01-24
2021-01-25
2021-01-26
2021-01-27
2021-01-28
2021-01-29
2021-01-30
2021-01-31
2021-02-01
2021-02-02
2021-02-03
2021-02-04
2021-02-05
2021-02-06
2021-02-07
2021-02-08
2021-02-09
2021-02-10
2021-02-11
2021-02-12
2021-02-13
2021-02-14
2021-02-15
2021-02-16
2021-02-17
2021-02-18
2021-02-19
2021-02-20
2021-02-21
2021-02-22
2021-02-23
2021-02-24
2021-02-25
2021-02-26
2021-02-27
2021-02-28
2021-03-01
2021-03-02
2021-03-03
2021-03-04
2021-03-05
2021-03-06
2021-03-07
2021-03-08
2021-03-09
2021-03-10
2021-03-11
2021-03-12
2021-03-13
2021-03-14
2021-03-15
2021-03-16
2021-03-17
2021-03-18
2021-03-19
2021-03-20
2021-03-21
2021-03-22
2021-03-23
2021-03-24
2021-03-25
2021-03-26
2021-03-27
2021-03-28
2021-03-29
2021-03-30
2021-03-31
2021-04-01
2021-04-02
2021-04-03
2021-04-04
2021-04-05
2021-04-06
2021-04-07
2021-04-08
2021-04-09
2021-04-10
2021-04-11
2021-04-12
2021-04-13
2021-04-14
2021-04-15
2021-04-16
2021-04-17
2021-04-18
2021-04-19
2021-04-20
2021-04-21
2021-04-22
2021-04-23
2021-04-24
2021-04-25
2021-04-26
2021-04-27
2021-04-28
2021-04-29
2021-04-30
2021-05-01
2021-05-02
2021-05-03
2021-05-04
2021-05-05
2021-05-06
2021-05-07
2021-05-08
2021-05-09
2021-05-10
2021-05-11
2021-05-12
2021-05-13
2021-05-14
2021-05-15
2021-05-16
2021-05-17
2021-05-18
2021-05-19
2021-05-20
2021-05-21
2021-05-22
2021-05-23
2021-05-24
2021-05-25
2021-05-26
2021-05-27
2021-05-28
2021-05-29
2021-05-30
2021-05-31
2021-06-01
2021-06-02
2021-06-03
2021-06-04
2021-06-05
2021-06-06
2021-06-07
2021-06-08
2021-06-09
2021-06-10
2021-06-11
2021-06-12
2021-06-13
2021-06-14
2021-06-15
2021-06-16
2021-06-17
2021-06-18
2021-06-19
2021-06-20
2021-06-21
2021-06-22
2021-06-23
2021-06-24
2021-06-25
2021-06-26
2021-06-27
2021-06-28
2021-06-29
2021-06-30
2021-07-01
2021-07-02
2021-07-03
2021-07-04
2021-07-05
2021-07-06
2021-07-07
2021-07-08
2021-07-09
2021-07-10
2021-07-11
2021-07-12
2021-07-13
2021-07-14
2021-07-15
2021-07-16
2021-07-17
2021-07-18
2021-07-19
2021-07-20
2021-07-21
2021-07-22
2021-07-23
2021-07-24
2021-07-25
2021-07-26
2021-07-27
2021-07-28
2021-07-29
2021-07-30
2021-07-31
2021-08-01
2021-08-02
2021-08-03
2021-08-04
2021-08-05
2021-08-06
2021-08-07
2021-08-08
2021-08-09
2021-08-10
2021-08-11
2021-08-12
2021-08-13
2021-08-14
2021-08-15
2021-08-16
2021-08-17
2021-08-18
2021-08-19
2021-08-20
2021-08-21
2021-08-22
2021-08-23
2021-08-24
2021-08-25
2021-08-26
2021-08-27
2021-08-28
2021-08-29
2021-08-30
2021-08-31
2021-09-01
2021-09-02
2021-09-03
2021-09-04
2021-09-05
2021-09-06
2021-09-07
2021-09-08
2021-09-09
2021-09-10
2021-09-11
2021-09-12
2021-09-13
2021-09-14
2021-09-15
2021-09-16
2021-09-17
2021-09-18
2021-09-19
2021-09-20
2021-09-21
2021-09-22
2021-09-23
2021-09-24
2021-09-25
2021-09-26
2021-09-27
2021-09-28
2021-09-29
2021-09-30
2021-10-01
2021-10-02
2021-10-03
2021-10-04
2021-10-05
2021-10-06
2021-10-07
2021-10-08
2021-10-09
2021-10-10
2021-10-11
2021-10-12
2021-10-13
2021-10-14
2021-10-15
2021-10-16
2021-10-17
2021-10-18
2021-10-19
2021-10-20
2021-10-21
2021-10-22
2021-10-23
2021-10-24
2021-10-25
2021-10-26
2021-10-27
2021-10-28
2021-10-29
2021-10-30
2021-10-31
2021-11-01
2021-11-02
2021-11-03
2021-11-04
2021-11-05
2021-11-06
2021-11-07
2021-11-08
2021-11-09
2021-11-10
2021-11-11
2021-11-12
2021-11-13
2021-11-14
2021-11-15
2021-11-16
2021-11-17
2021-11-18
2021-11-19
2021-11-20
2021-11-21
2021-11-22
2021-11-23
2021-11-24
2021-11-25
2021-11-26
2021-11-27
2021-11-28
2021-11-29
2021-11-30
2021-12-01
2021-12-02
2021-12-03
2021-12-04
2021-12-05
2021-12-06
2021-12-07
2021-12-08
2021-12-09
2021-12-10
2021-12-11
2021-12-12
2021-12-13
2021-12-14
2021-12-15
2021-12-16
2021-12-17
2021-12-18
2021-12-19
2021-12-20
2021-12-21
2021-12-22
2021-12-23
2021-12-24
2021-12-25
2021-12-26
2021-12-27
2021-12-28
2021-12-29
2021-12-30
2021-12-31
2022-01-01
2022-01-02
2022-01-03
2022-01-04
2022-01-05
2022-01-06
2022-01-07
2022-01-08
2022-01-09
2022-01-10
2022-01-11
2022-01-12
2022-01-13
2022-01-14
2022-01-15
2022-01-16
2022-01-17
2022-01-18
2022-01-19
2022-01-20
2022-01-21
2022-01-22
2022-01-23
2022-01-24
2022-01-25
2022-01-26
2022-01-27
2022-01-28
2022-01-29
2022-01-30
2022-01-31
2022-02-01
2022-02-02
2022-02-03
2022-02-04
2022-02-05
2022-02-06
2022-02-07
2022-02-08
2022-02-09
2022-02-10
2022-02-11
2022-02-12
2022-02-13
2022-02-14
2022-02-15
2022-02-16
2022-02-17
2022-02-18
2022-02-19
2022-02-20
2022-02-21
2022-02-22
2022-02-23
2022-02-24
2022-02-25
2022-02-26
2022-02-27
2022-02-28
2022-03-01
2022-03-02
2022-03-03
2022-03-04
2022-03-05
2022-03-06
2022-03-07
2022-03-08
2022-03-09
2022-03-10
2022-03-11
2022-03-12
2022-03-13
2022-03-14
2022-03-15
2022-03-16
2022-03-17
2022-03-18
2022-03-19
2022-03-20
2022-03-21
2022-03-22
2022-03-23
2022-03-24
2022-03-25
2022-03-26
2022-03-27
2022-03-28
2022-03-29
2022-03-30
2022-03-31
2022-04-01
2022-04-02
2022-04-03
2022-04-04
2022-04-05
2022-04-06
2022-04-07
2022-04-08
2022-04-09
2022-04-10
2022-04-11
2022-04-12
2022-04-13
2022-04-14
2022-04-15
2022-04-16
2022-04-17
2022-04-18
2022-04-19
2022-04-20
2022-04-21
2022-04-22
2022-04-23
2022-04-24
2022-04-25
2022-04-26
2022-04-27
2022-04-28
2022-04-29
2022-04-30
2022-05-01
2022-05-02
2022-05-03
2022-05-04
2022-05-05
2022-05-06
2022-05-07
2022-05-08
2022-05-09
2022-05-10
2022-05-11
2022-05-12
2022-05-13
2022-05-14
2022-05-15
2022-05-16
2022-05-17
2022-05-18
2022-05-19
2022-05-20
2022-05-21
2022-05-22
2022-05-23
2022-05-24
2022-05-25
2022-05-26
2022-05-27
2022-05-28
2022-05-29
2022-05-30
2022-05-31
2022-06-01
2022-06-02
2022-06-03
2022-06-04
2022-06-05
2022-06-06
2022-06-07
2022-06-08
2022-06-09
2022-06-10
2022-06-11
2022-06-12
2022-06-13
2022-06-14
2022-06-15
2022-06-16
2022-06-17
2022-06-18
2022-06-19
2022-06-20
2022-06-21
2022-06-22
2022-06-23
2022-06-24
2022-06-25
2022-06-26
2022-06-27
2022-06-28
2022-06-29
2022-06-30
2022-07-01
2022-07-02
2022-07-03
2022-07-04
2022-07-05
2022-07-06
2022-07-07
2022-07-08
2022-07-09
2022-07-10
2022-07-11
2022-07-12
2022-07-13
2022-07-14
2022-07-15
2022-07-16
2022-07-17
2022-07-18
2022-07-19
2022-07-20
2022-07-21
2022-07-22
2022-07-23
2022-07-24
2022-07-25
2022-07-26
2022-07-27
2022-07-28
2022-07-29
2022-07-30
2022-07-31
2022-08-01
2022-08-02
2022-08-03
2022-08-04
2022-08-05
2022-08-06
2022-08-07
2022-08-08
2022-08-09
2022-08-10
2022-08-11
2022-08-12
2022-08-13
2022-08-14
2022-08-15
2022-08-16
2022-08-17
2022-08-18
2022-08-19
2022-08-20
2022-08-21
2022-08-22
2022-08-23
2022-08-24
2022-08-25
2022-08-26
2022-08-27
2022-08-28
2022-08-29
2022-08-30
2022-08-31
2022-09-01
2022-09-02
2022-09-03
2022-09-04
2022-09-05
2022-09-06
2022-09-07
2022-09-08
2022-09-09
2022-09-10
2022-09-11
2022-09-12
2022-09-13
2022-09-14
2022-09-15
2022-09-16
2022-09-17
2022-09-18
2022-09-19
2022-09-20
2022-09-21
2022-09-22
2022-09-23
2022-09-24
2022-09-25
2022-09-26
2022-09-27
2022-09-28
2022-09-29
2022-09-30
2022-10-01
2022-10-02
2022-10-03
2022-10-04
2022-10-05
2022-10-06
2022-10-07
2022-10-08
2022-10-09
2022-10-10
2022-10-11
2022-10-12
2022-10-13
2022-10-14
2022-10-15
2022-10-16
2022-10-17
2022-10-18
2022-10-19
2022-10-20
2022-10-21
2022-10-22
2022-10-23
2022-10-24
2022-10-25
2022-10-26
2022-10-27
2022-10-28
2022-10-29
2022-10-30
2022-10-31
2022-11-01
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31
2023-02-01
2023-02-02
2023-02-03
2023-02-04
2023-02-05
2023-02-06
2023-02-07
2023-02-08
2023-02-09
2023-02-10
2023-02-11
2023-02-12
2023-02-13
2023-02-14
2023-02-15
2023-02-16
2023-02-17
2023-02-18
2023-02-19
2023-02-20
2023-02-21
2023-02-22
2023-02-23
2023-02-24
2023-02-25
2023-02-26
2023-02-27
2023-02-28
2023-03-01
2023-03-02
2023-03-03
2023-03-04
2023-03-05
2023-03-06
2023-03-07
2023-03-08
2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-03-13
2023-03-14
2023-03-15
2023-03-16
2023-03-17
2023-03-18
2023-03-19
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-25
2023-03-26
2023-03-27
2023-03-28
2023-03-29
2023-03-30
2023-03-31
2023-04-01
2023-04-02
2023-04-03
2023-04-04
2023-04-05
2023-04-06
2023-04-07
2023-04-08
2023-04-09
2023-04-10
2023-04-11
2023-04-12
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24
2023-04-25
2023-04-26
2023-04-27
2023-04-28
2023-04-29
2023-04-30
2023-05-01
2023-05-02
2023-05-03
2023-05-04
2023-05-05
2023-05-06
2023-05-07
2023-05-08
2023-05-09
2023-05-10
2023-05-11
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16
2023-05-17
2023-05-18
2023-05-19
2023-05-20
2023-05-21
2023-05-22
2023-05-23
2023-05-24
2023-05-25
2023-05-26
2023-05-27
2023-05-28
2023-05-29
2023-05-30
2023-05-31
2023-06-01
2023-06-02
2023-06-03
2023-06-04
2023-06-05
2023-06-06
2023-06-07
2023-06-08
2023-06-09
2023-06-10
2023-06-11
2023-06-12
2023-06-13
2023-06-14
2023-06-15
2023-06-16
2023-06-17
2023-06-18
2023-06-19
2023-06-20
2023-06-21
2023-06-22
2023-06-23
2023-06-24
2023-06-25
2023-06-26
2023-06-27
2023-06-28
2023-06-29
2023-06-30
2023-07-01
2023-07-02
2023-07-03
2023-07-04
2023-07-05
2023-07-06
2023-07-07
2023-07-08
2023-07-09
2023-07-10
2023-07-11
2023-07-12
2023-07-13
2023-07-14
2023-07-15
2023-07-16
2023-07-17
2023-07-18
2023-07-19
2023-07-20
2023-07-21
2023-07-22
2023-07-23
2023-07-24
2023-07-25
2023-07-26
2023-07-27
2023-07-28
2023-07-29
2023-07-30
2023-07-31
2023-08-01
2023-08-02
2023-08-03
2023-08-04
2023-08-05
2023-08-06
2023-08-07
2023-08-08
2023-08-09
2023-08-10
2023-08-11
2023-08-12
2023-08-13
2023-08-14
2023-08-15
2023-08-16
2023-08-17
2023-08-18
2023-08-19
2023-08-20
2023-08-21
2023-08-22
2023-08-23
2023-08-24
2023-08-25
2023-08-26
2023-08-27
2023-08-28
2023-08-29
2023-08-30
2023-08-31
2023-09-01
2023-09-02
2023-09-03
2023-09-04
2023-09-05
2023-09-06
2023-09-07
2023-09-08
2023-09-09
2023-09-10
2023-09-11
2023-09-12
2023-09-13
2023-09-14
2023-09-15
2023-09-16
2023-09-17
2023-09-18
2023-09-19
2023-09-20
2023-09-21
2023-09-22
2023-09-23
2023-09-24
2023-09-25
2023-09-26
2023-09-27
2023-09-28
2023-09-29
2023-09-30
2023-10-01
2023-10-02
2023-10-03
2023-10-04
2023-10-05
2023-10-06
2023-10-07
2023-10-08
2023-10-09
2023-10-10
2023-10-11
2023-10-12
2023-10-13
2023-10-14
2023-10-15
2023-10-16
2023-10-17
2023-10-18
2023-10-19
2023-10-20
2023-10-21
2023-10-22
2023-10-23
2023-10-24
2023-10-25
2023-10-26
2023-10-27
2023-10-28
2023-10-29
2023-10-30
2023-10-31
2023-11-01
2023-11-02
2023-11-03
2023-11-04
2023-11-05
2023-11-06
2023-11-07
2023-11-08
2023-11-09
2023-11-10
2023-11-11
2023-11-12
2023-11-13
2023-11-14
2023-11-15
2023-11-16
2023-11-17
2023-11-18
2023-11-19
2023-11-20
2023-11-21
2023-11-22
2023-11-23
2023-11-24
2023-11-25
2023-11-26
2023-11-27
2023-11-28
2023-11-29
2023-11-30
2023-12-01
2023-12-02
2023-12-03
2023-12-04
2023-12-05
2023-12-06
2023-12-07
2023-12-08
2023-12-09
2023-12-10
2023-12-11
2023-12-12
2023-12-13
2023-12-14
2023-12-15
2023-12-16
2023-12-17
2023-12-18
2023-12-19
2023-12-20
2023-12-21
2023-12-22
2023-12-23
2023-12-24
2023-12-25
2023-12-26
2023-12-27
2023-12-28
2023-12-29
2023-12-30
2023-12-31
2024-01-01
2024-01-02
2024-01-03
2024-01-04
2024-01-05
2024-01-06
2024-01-07
2024-01-08
2024-01-09
2024-01-10
2024-01-11
2024-01-12
2024-01-13
2024-01-14
2024-01-15
2024-01-16
2024-01-17
2024-01-18
2024-01-19
2024-01-20
2024-01-21
2024-01-22
2024-01-23
2024-01-24
2024-01-25
2024-01-26
2024-01-27
2024-01-28
2024-01-29
2024-01-30
2024-01-31
2024-02-01
2024-02-02
2024-02-03
2024-02-04
2024-02-05
2024-02-06
2024-02-07
2024-02-08
2024-02-09
2024-02-10
2024-02-11
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17
2024-02-18
2024-02-19
2024-02-20
2024-02-21
2024-02-22
2024-02-23
2024-02-24
2024-02-25
2024-02-26
2024-02-27
2024-02-28
2024-02-29
2024-03-01
2024-03-02
2024-03-03
2024-03-04
2024-03-05
2024-03-06
2024-03-07
2024-03-08
2024-03-09
2024-03-10
2024-03-11
2024-03-12
2024-03-13
2024-03-14
2024-03-15
2024-03-16
2024-03-17
2024-03-18
2024-03-19
2024-03-20
2024-03-21
2024-03-22
2024-03-23
2024-03-24
2024-03-25
2024-03-26
2024-03-27
2024-03-28
2024-03-29
2024-03-30
2024-03-31
2024-04-01
2024-04-02
2024-04-03
2024-04-04
2024-04-05
2024-04-06
2024-04-07
2024-04-08
2024-04-09
2024-04-10
2024-04-11
2024-04-12
2024-04-13
2024-04-14
2024-04-15
2024-04-16
2024-04-17
2024-04-18
2024-04-19
2024-04-20
2024-04-21
2024-04-22
2024-04-23
2024-04-24
2024-04-25
2024-04-26
2024-04-27
2024-04-28
2024-04-29
2024-04-30
2024-05-01
2024-05-02
2024-05-03
2024-05-04
2024-05-05
2024-05-06
2024-05-07
2024-05-08
2024-05-09
2024-05-10
2024-05-11
2024-05-12
2024-05-13
2024-05-14
2024-05-15
2024-05-16
2024-05-17
2024-05-18
2024-05-19
2024-05-20
2024-05-21
2024-05-22
2024-05-23
2024-05-24
2024-05-25
2024-05-26
2024-05-27
2024-05-28
2024-05-29
2024-05-30
2024-05-31
2024-06-01
2024-06-02
2024-06-03
2024-06-04
2024-06-05
2024-06-06
2024-06-07
2024-06-08
2024-06-09
2024-06-10
2024-06-11
2024-06-12
2024-06-13
2024-06-14
2024-06-15
2024-06-16
2024-06-17
2024-06-18
2024-06-19
2024-06-20
2024-06-21
2024-06-22
2024-06-23
2024-06-24
2024-06-25
2024-06-26
2024-06-27
2024-06-28
2024-06-29
2024-06-30
2024-07-01
2024-07-02
2024-07-03
2024-07-04
2024-07-05
2024-07-06
2024-07-07
2024-07-08
2024-07-09
2024-07-10
2024-07-11
2024-07-12
2024-07-13
2024-07-14
2024-07-15
2024-07-16
2024-07-17
2024-07-18
2024-07-19
2024-07-20
2024-07-21
2024-07-22
2024-07-23
2024-07-24
2024-07-25
2024-07-26
2024-07-27
2024-07-28
2024-07-29
2024-07-30
2024-07-31
2024-08-01
2024-08-02
2024-08-03
2024-08-04
2024-08-05
2024-08-06
2024-08-07
2024-08-08
2024-08-09
2024-08-10
2024-08-11
2024-08-12
2024-08-13
2024-08-14
2024-08-15
2024-08-16
2024-08-17
2024-08-18
2024-08-19
2024-08-20
2024-08-21
2024-08-22
2024-08-23
2024-08-24
2024-08-25
2024-08-26
2024-08-27
2024-08-28
2024-08-29
2024-08-30
2024-08-31
2024-09-01
2024-09-02
2024-09-03
2024-09-04
2024-09-05
2024-09-06
2024-09-07
2024-09-08
2024-09-09
2024-09-10
2024-09-11
2024-09-12
2024-09-13
2024-09-14
2024-09-15
2024-09-16
2024-09-17
2024-09-18
2024-09-19
2024-09-20
2024-09-21
2024-09-22
2024-09-23
2024-09-24
2024-09-25
2024-09-26
2024-09-27
2024-09-28
2024-09-29
2024-09-30
2024-10-01
2024-10-02
2024-10-03
2024-10-04
2024-10-05
2024-10-06
2024-10-07
2024-10-08
2024-10-09
2024-10-10
2024-10-11
2024-10-12
2024-10-13
2024-10-14
2024-10-15
2024-10-16
2024-10-17
2024-10-18
2024-10-19
2024-10-20
2024-10-21
2024-10-22
2024-10-23
2024-10-24
2024-10-25
2024-10-26
2024-10-27
2024-10-28
2024-10-29
2024-10-30
2024-10-31
2024-11-01
2024-11-02
2024-11-03
2024-11-04
2024-11-05
2024-11-06
2024-11-07
2024-11-08
2024-11-09
2024-11-10
2024-11-11
2024-11-12
2024-11-13
2024-11-14
2024-11-15
2024-11-16
2024-11-17
2024-11-18
2024-11-19
2024-11-20
2024-11-21
2024-11-22
2024-11-23
2024-11-24
2024-11-25
2024-11-26
2024-11-27
2024-11-28
2024-11-29
2024-11-30
2024-12-01
2024-12-02
2024-12-03
2024-12-04
2024-12-05
2024-12-06
2024-12-07
2024-12-08
2024-12-09
2024-12-10
2024-12-11
2024-12-12
2024-12-13
2024-12-14
2024-12-15
2024-12-16
2024-12-17
2024-12-18
2024-12-19
2024-12-20
2024-12-21
2024-12-22
2024-12-23
2024-12-24
2024-12-25
2024-12-26
2024-12-27
2024-12-28
2024-12-29
2024-12-30
2024-12-31
2025-01-01
2025-01-02
2025-01-03
2025-01-04
2025-01-05
2025-01-06
2025-01-07
2025-01-08
2025-01-09
2025-01-10
2025-01-11
2025-01-12
2025-01-13
2025-01-14
2025-01-15
2025-01-16
2025-01-17
2025-01-18
2025-01-19
2025-01-20
2025-01-21
2025-01-22
2025-01-23
2025-01-24
2025-01-25
2025-01-26
2025-01-27
2025-01-28
2025-01-29
2025-01-30
2025-01-31
2025-02-01
2025-02-02
2025-02-03
2025-02-04
2025-02-05
2025-02-06
2025-02-07
2025-02-08
2025-02-09
2025-02-10
2025-02-11
2025-02-12
2025-02-13
2025-02-14
2025-02-15
2025-02-16
2025-02-17
2025-02-18
2025-02-19
2025-02-20
2025-02-21
2025-02-22
2025-02-23
2025-02-24
2025-02-25
2025-02-26
2025-02-27
2025-02-28
2025-03-01
2025-03-02
2025-03-03
2025-03-04
2025-03-05
2025-03-06
2025-03-07
2025-03-08
2025-03-09
2025-03-10
2025-03-11
2025-03-12
2025-03-13
2025-03-14
2025-03-15
2025-03-16
2025-03-17
2025-03-18
2025-03-19
2025-03-20
2025-03-21
2025-03-22
2025-03-23
2025-03-24
2025-03-25
2025-03-26
2025-03-27
2025-03-28
2025-03-29
2025-03-30
2025-03-31
2025-04-01
2025-04-02
2025-04-03
2025-04-04
2025-04-05
2025-04-06
2025-04-07
2025-04-08
2025-04-09
2025-04-10
2025-04-11
2025-04-12
2025-04-13
2025-04-14
2025-04-15
2025-04-16
2025-04-17
2025-04-18
2025-04-19
2025-04-20
2025-04-21
2025-04-22
2025-04-23
2025-04-24
2025-04-25
2025-04-26
2025-04-27
2025-04-28
2025-04-29
2025-04-30
2025-05-01
2025-05-02
2025-05-03
2025-05-04
2025-05-05
2025-05-06
2025-05-07
2025-05-08
2025-05-09
2025-05-10
2025-05-11
2025-05-12
2025-05-13
2025-05-14
2025-05-15
2025-05-16
2025-05-17
2025-05-18
2025-05-19
2025-05-20
2025-05-21
2025-05-22
2025-05-23
2025-05-24
2025-05-25
2025-05-26
2025-05-27
2025-05-28
2025-05-29
2025-05-30
2025-05-31
2025-06-01
2025-06-02
2025-06-03
2025-06-04
2025-06-05
2025-06-06
2025-06-07
2025-06-08
2025-06-09
2025-06-10
2025-06-11
2025-06-12
2025-06-13
2025-06-14
2025-06-15
2025-06-16
2025-06-17
2025-06-18
2025-06-19
2025-06-20
2025-06-21
2025-06-22
2025-06-23
2025-06-24
2025-06-25
2025-06-26
2025-06-27
2025-06-28
2025-06-29
2025-06-30
2025-07-01
2025-07-02
2025-07-03
2025-07-04
2025-07-05
2025-07-06
2025-07-07
2025-07-08
2025-07-09
2025-07-10
2025-07-11
2025-07-12
2025-07-13
2025-07-14
2025-07-15
2025-07-16
2025-07-17
2025-07-18
2025-07-19
2025-07-20
2025-07-21
2025-07-22
2025-07-23
2025-07-24
2025-07-25
2025-07-26
2025-07-27
2025-07-28
2025-07-29
2025-07-30
2025-07-31
2025-08-01
2025-08-02
2025-08-03
2025-08-04
2025-08-05
2025-08-06
2025-08-07
2025-08-08
2025-08-09
2025-08-10
2025-08-11
2025-08-12
2025-08-13
2025-08-14
2025-08-15
2025-08-16
2025-08-17
2025-08-18
2025-08-19
2025-08-20
2025-08-21
2025-08-22
2025-08-23
2025-08-24
2025-08-25
2025-08-26
2025-08-27
2025-08-28
2025-08-29
2025-08-30
2025-08-31
2025-09-01
2025-09-02
2025-09-03
2025-09-04
2025-09-05
2025-09-06
2025-09-07
2025-09-08
2025-09-09
2025-09-10
2025-09-11
2025-09-12
2025-09-13
2025-09-14
2025-09-15
2025-09-16
2025-09-17
2025-09-18
2025-09-19
2025-09-20
2025-09-21
2025-09-22
2025-09-23
2025-09-24
2025-09-25
2025-09-26
2025-09-27
2025-09-28
2025-09-29
2025-09-30
2025-10-01
2025-10-02
2025-10-03
2025-10-04
2025-10-05
2025-10-06
2025-10-07
2025-10-08
2025-10-09
2025-10-10
2025-10-11
2025-10-12
2025-10-13
2025-10-14
2025-10-15
2025-10-16
2025-10-17
2025-10-18
2025-10-19
2025-10-20
2025-10-21
2025-10-22
2025-10-23
2025-10-24
2025-10-25
2025-10-26
2025-10-27
2025-10-28
2025-10-29
2025-10-30
2025-10-31
2025-11-01
2025-11-02
2025-11-03
2025-11-04
2025-11-05
2025-11-06
2025-11-07
2025-11-08
2025-11-09
2025-11-10
2025-11-11
2025-11-12
2025-11-13
2025-11-14
2025-11-15
2025-11-16
2025-11-17
2025-11-18
2025-11-19
2025-11-20
2025-11-21
2025-11-22
2025-11-23
2025-11-24
2025-11-25
2025-11-26
2025-11-27
2025-11-28
2025-11-29
2025-11-30
2025-12-01
2025-12-02
2025-12-03
2025-12-04
2025-12-05
2025-12-06
2025-12-07
2025-12-08
2025-12-09
2025-12-10
2025-12-11
2025-12-12
2025-12-13
2025-12-14
2025-12-15
2025-12-16
2025-12-17
2025-12-18
2025-12-19
2025-12-20
2025-12-21
2025-12-22
2025-12-23
2025-12-24
2025-12-25
2025-12-26
2025-12-27
2025-12-28
2025-12-29
2025-12-30
2025-12-31
2026-01-01
2026-01-02
2026-01-03
2026-01-04
2026-01-05
2026-01-06
2026-01-07
2026-01-08
2026-01-09
2026-01-10
2026-01-11
2026-01-12
2026-01-13
2026-01-14
2026-01-15
2026-01-16
2026-01-17
2026-01-18
2026-01-19
2026-01-20
2026-01-21
2026-01-22
2026-01-23
2026-01-24
2026-01-25
2026-01-26
2026-01-27
2026-01-28
2026-01-29
2026-01-30
2026-01-31
2026-02-01
2026-02-02
2026-02-03
2026-02-04
2026-02-05
2026-02-06
2026-02-07
2026-02-08
2026-02-09
2026-02-10
2026-02-11
2026-02-12
2026-02-13
2026-02-14
2026-02-15
2026-02-16
2026-02-17
2026-02-18
2026-02-19
2026-02-20
2026-02-21
2026-02-22
2026-02-23
2026-02-24
2026-02-25
2026-02-26
2026-02-27
2026-02-28
2026-03-01
2026-03-02
2026-03-03
2026-03-04
2026-03-05
2026-03-06
2026-03-07
2026-03-08
2026-03-09
2026-03-10
2026-03-11
2026-03-12
2026-03-13
2026-03-14
2026-03-15
2026-03-16
2026-03-17
2026-03-18
2026-03-19
2026-03-20
2026-03-21
2026-03-22
2026-03-23
2026-03-24
2026-03-25
2026-03-26
2026-03-27
2026-03-28
2026-03-29
2026-03-30
2026-03-31
2026-04-01
2026-04-02
2026-04-03
2026-04-04
2026-04-05
2026-04-06
2026-04-07
2026-04-08
2026-04-09
2026-04-10
2026-04-11
2026-04-12
2026-04-13
2026-04-14
2026-04-15
2026-04-16
2026-04-17
2026-04-18
2026-04-19
2026-04-20
2026-04-21
2026-04-22
2026-04-23
2026-04-24
2026-04-25
2026-04-26
2026-04-27
2026-04-28
2026-04-29
2026-04-30
2026-05-01
2026-05-02
2026-05-03
2026-05-04
2026-05-05
2026-05-06
2026-05-07
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
2026-05-18
2026-05-19
2026-05-20
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
2026-05-31
2026-06-01
2026-06-02
2026-06-03
2026-06-04
2026-06-05
2026-06-06
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20
2026-06-21
2026-06-22
2026-06-23
2026-06-24
2026-06-25
2026-06-26
2026-06-27
2026-06-28
2026-06-29
2026-06-30
2026-07-01
2026-07-02
2026-07-03
2026-07-04
2026-07-05
2026-07-06
2026-07-07
2026-07-08
2026-07-09
2026-07-10
2026-07-11
2026-07-12
2026-07-13
2026-07-14
2026-07-15
2026-07-16
2026-07-17
2026-07-18
2026-07-19
2026-07-20
2026-07-21
2026-07-22
2026-07-23
2026-07-24
2026-07-25
2026-07-26
2026-07-27
2026-07-28
2026-07-29
2026-07-30
2026-07-31
2026-08-01
2026-08-02
2026-08-03
2026-08-04
2026-08-05
2026-08-06
2026-08-07
2026-08-08
2026-08-09
2026-08-10
2026-08-11
2026-08-12
2026-08-13
2026-08-14
2026-08-15
2026-08-16
2026-08-17
2026-08-18
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-23
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-30
2026-08-31
2026-09-01
2026-09-02
2026-09-03
2026-09-04
2026-09-05
2026-09-06
2026-09-07
2026-09-08
2026-09-09
2026-09-10
2026-09-11
2026-09-12
2026-09-13
2026-09-14
2026-09-15
2026-09-16
2026-09-17
2026-09-18
2026-09-19
2026-09-20
2026-09-21
2026-09-22
2026-09-23
2026-09-24
2026-09-25
2026-09-26
2026-09-27
2026-09-28
2026-09-29
2026-09-30
2026-10-01
2026-10-02
2026-10-03
2026-10-04
2026-10-05
2026-10-06
2026-10-07
2026-10-08
2026-10-09
2026-10-10
2026-10-11
2026-10-12
2026-10-13
2026-10-14
2026-10-15
2026-10-16
2026-10-17
2026-10-18
2026-10-19
2026-10-20
2026-10-21
2026-10-22
2026-10-23
2026-10-24
2026-10-25
2026-10-26
2026-10-27
2026-10-28
2026-10-29
2026-10-30
2026-10-31
2026-11-01
2026-11-02
2026-11-03
2026-11-04
2026-11-05
2026-11-06
2026-11-07
2026-11-08
2026-11-09
2026-11-10
2026-11-11
2026-11-12
2026-11-13
2026-11-14
2026-11-15
2026-11-16
2026-11-17
2026-11-18
2026-11-19
2026-11-20
2026-11-21
2026-11-22
2026-11-23
2026-11-24
2026-11-25
2026-11-26
2026-11-27
2026-11-28
2026-11-29
2026-11-30
2026-12-01
2026-12-02
2026-12-03
2026-12-04
2026-12-05
2026-12-06
2026-12-07
2026-12-08
2026-12-09
2026-12-10
2026-12-11
2026-12-12
2026-12-13
2026-12-14
2026-12-15
2026-12-16
2026-12-17
2026-12-18
2026-12-19
2026-12-20
2026-12-21
2026-12-22
2026-12-23
2026-12-24
2026-12-25
2026-12-26
2026-12-27
2026-12-28
2026-12-29
2026-12-30
2026-12-31
2027-01-01
2027-01-02
2027-01-03
2027-01-04
2027-01-05
2027-01-06
2027-01-07
2027-01-08
2027-01-09
2027-01-10
2027-01-11
2027-01-12
2027-01-13
2027-01-14
2027-01-15
2027-01-16
2027-01-17
2027-01-18
2027-01-19
2027-01-20
2027-01-21
2027-01-22
2027-01-23
2027-01-24
2027-01-25
2027-01-26
2027-01-27
2027-01-28
2027-01-29
2027-01-30
2027-01-31
2027-02-01
2027-02-02
2027-02-03
2027-02-04
2027-02-05
2027-02-06
2027-02-07
2027-02-08
2027-02-09
2027-02-10
2027-02-11
2027-02-12
2027-02-13
2027-02-14
2027-02-15
2027-02-16
2027-02-17
2027-02-18
2027-02-19
2027-02-20
2027-02-21
2027-02-22
2027-02-23
2027-02-24
2027-02-25
2027-02-26
2027-02-27
2027-02-28
2027-03-01
2027-03-02
2027-03-03
2027-03-04
2027-03-05
2027-03-06
2027-03-07
2027-03-08
2027-03-09
2027-03-10
2027-03-11
2027-03-12
2027-03-13
2027-03-14
2027-03-15
2027-03-16
2027-03-17
2027-03-18
2027-03-19
2027-03-20
2027-03-21
2027-03-22
2027-03-23
2027-03-24
2027-03-25
2027-03-26
2027-03-27
2027-03-28
2027-03-29
2027-03-30
2027-03-31
2027-04-01
2027-04-02
2027-04-03
2027-04-04
2027-04-05
2027-04-06
2027-04-07
2027-04-08
2027-04-09
2027-04-10
2027-04-11
2027-04-12
2027-04-13
2027-04-14
2027-04-15
2027-04-16
2027-04-17
2027-04-18
2027-04-19
2027-04-20
2027-04-21
2027-04-22
2027-04-23
2027-04-24
2027-04-25
2027-04-26
2027-04-27
2027-04-28
2027-04-29
2027-04-30
2027-05-01
2027-05-02
2027-05-03
2027-05-04
2027-05-05
2027-05-06
2027-05-07
2027-05-08
2027-05-09
2027-05-10
2027-05-11
2027-05-12
2027-05-13
2027-05-14
2027-05-15
2027-05-16
2027-05-17
2027-05-18
2027-05-19
2027-05-20
2027-05-21
2027-05-22
2027-05-23
2027-05-24
2027-05-25
2027-05-26
2027-05-27
2027-05-28
2027-05-29
2027-05-30
2027-05-31
2027-06-01
2027-06-02
2027-06-03
2027-06-04
2027-06-05
2027-06-06
2027-06-07
2027-06-08
2027-06-09
2027-06-10
2027-06-11
2027-06-12
2027-06-13
2027-06-14
2027-06-15
2027-06-16
2027-06-17
2027-06-18
2027-06-19
2027-06-20
2027-06-21
2027-06-22
2027-06-23
2027-06-24
2027-06-25
2027-06-26
2027-06-27
2027-06-28
2027-06-29
2027-06-30
2027-07-01
2027-07-02
2027-07-03
2027-07-04
2027-07-05
2027-07-06
2027-07-07
2027-07-08
2027-07-09
2027-07-10
2027-07-11
2027-07-12
2027-07-13
2027-07-14
2027-07-15
2027-07-16
2027-07-17
2027-07-18
2027-07-19
2027-07-20
2027-07-21
2027-07-22
2027-07-23
2027-07-24
2027-07-25
2027-07-26
2027-07-27
2027-07-28
2027-07-29
2027-07-30
2027-07-31
2027-08-01
2027-08-02
2027-08-03
2027-08-04
2027-08-05
2027-08-06
2027-08-07
2027-08-08
2027-08-09
2027-08-10
2027-08-11
2027-08-12
2027-08-13
2027-08-14
2027-08-15
2027-08-16
2027-08-17
2027-08-18
2027-08-19
2027-08-20
2027-08-21
2027-08-22
2027-08-23
2027-08-24
2027-08-25
2027-08-26
2027-08-27
2027-08-28
2027-08-29
2027-08-30
2027-08-31
2027-09-01
2027-09-02
2027-09-03
2027-09-04
2027-09-05
2027-09-06
2027-09-07
2027-09-08
2027-09-09
2027-09-10
2027-09-11
2027-09-12
2027-09-13
2027-09-14
2027-09-15
2027-09-16
2027-09-17
2027-09-18
2027-09-19
2027-09-20
2027-09-21
2027-09-22
2027-09-23
2027-09-24
2027-09-25
2027-09-26
2027-09-27
2027-09-28
2027-09-29
2027-09-30
2027-10-01
2027-10-02
2027-10-03
2027-10-04
2027-10-05
2027-10-06
2027-10-07
2027-10-08
2027-10-09
2027-10-10
2027-10-11
2027-10-12
2027-10-13
2027-10-14
2027-10-15
2027-10-16
2027-10-17
2027-10-18
2027-10-19
2027-10-20
2027-10-21
2027-10-22
2027-10-23
2027-10-24
2027-10-25
2027-10-26
2027-10-27
2027-10-28
2027-10-29
2027-10-30
2027-10-31
2027-11-01
2027-11-02
2027-11-03
2027-11-04
2027-11-05
2027-11-06
2027-11-07
2027-11-08
2027-11-09
2027-11-10
2027-11-11
2027-11-12
2027-11-13
2027-11-14
2027-11-15
2027-11-16
2027-11-17
2027-11-18
2027-11-19
2027-11-20
2027-11-21
2027-11-22
2027-11-23
2027-11-24
2027-11-25
2027-11-26
2027-11-27
2027-11-28
2027-11-29
2027-11-30
2027-12-01
2027-12-02
2027-12-03
2027-12-04
2027-12-05
2027-12-06
2027-12-07
2027-12-08
2027-12-09
2027-12-10
2027-12-11
2027-12-12
2027-12-13
2027-12-14
2027-12-15
2027-12-16
2027-12-17
2027-12-18
2027-12-19
2027-12-20
2027-12-21
2027-12-22
2027-12-23
2027-12-24
2027-12-25
2027-12-26
2027-12-27
2027-12-28
2027-12-29
2027-12-30
2027-12-31
2028-01-01
2028-01-02
2028-01-03
2028-01-04
2028-01-05
2028-01-06
2028-01-07
2028-01-08
2028-01-09
2028-01-10
2028-01-11
2028-01-12
2028-01-13
2028-01-14
2028-01-15
2028-01-16
2028-01-17
2028-01-18
2028-01-19
2028-01-20
2028-01-21
2028-01-22
2028-01-23
2028-01-24
2028-01-25
2028-01-26
2028-01-27
2028-01-28
2028-01-29
2028-01-30
2028-01-31
2028-02-01
2028-02-02
2028-02-03
2028-02-04
2028-02-05
2028-02-06
2028-02-07
2028-02-08
2028-02-09
2028-02-10
2028-02-11
2028-02-12
2028-02-13
2028-02-14
2028-02-15
2028-02-16
2028-02-17
2028-02-18
2028-02-19
2028-02-20
2028-02-21
2028-02-22
2028-02-23
2028-02-24
2028-02-25
2028-02-26
2028-02-27
2028-02-28
2028-02-29
2028-03-01
2028-03-02
2028-03-03
2028-03-04
2028-03-05
2028-03-06
2028-03-07
2028-03-08
2028-03-09
2028-03-10
2028-03-11
2028-03-12
2028-03-13
2028-03-14
2028-03-15
2028-03-16
2028-03-17
2028-03-18
2028-03-19
2028-03-20
2028-03-21
2028-03-22
2028-03-23
2028-03-24
2028-03-25
2028-03-26
2028-03-27
2028-03-28
2028-03-29
2028-03-30
2028-03-31
2028-04-01
2028-04-02
2028-04-03
2028-04-04
2028-04-05
2028-04-06
2028-04-07
2028-04-08
2028-04-09
2028-04-10
2028-04-11
2028-04-12
2028-04-13
2028-04-14
2028-04-15
2028-04-16
2028-04-17
2028-04-18
2028-04-19
2028-04-20
2028-04-21
2028-04-22
2028-04-23
2028-04-24
2028-04-25
2028-04-26
2028-04-27
2028-04-28
2028-04-29
2028-04-30
2028-05-01
2028-05-02
2028-05-03
2028-05-04
2028-05-05
2028-05-06
2028-05-07
2028-05-08
2028-05-09
2028-05-10
2028-05-11
2028-05-12
2028-05-13
2028-05-14
2028-05-15
2028-05-16
2028-05-17
2028-05-18
2028-05-19
2028-05-20
2028-05-21
2028-05-22
2028-05-23
2028-05-24
2028-05-25
2028-05-26
2028-05-27
2028-05-28
2028-05-29
2028-05-30
2028-05-31
2028-06-01
2028-06-02
2028-06-03
2028-06-04
2028-06-05
2028-06-06
2028-06-07
2028-06-08
2028-06-09
2028-06-10
2028-06-11
2028-06-12
2028-06-13
2028-06-14
2028-06-15
2028-06-16
2028-06-17
2028-06-18
2028-06-19
2028-06-20
2028-06-21
2028-06-22
2028-06-23
2028-06-24
2028-06-25
2028-06-26
2028-06-27
2028-06-28
2028-06-29
2028-06-30
2028-07-01
2028-07-02
2028-07-03
2028-07-04
2028-07-05
2028-07-06
2028-07-07
2028-07-08
2028-07-09
2028-07-10
2028-07-11
2028-07-12
2028-07-13
2028-07-14
2028-07-15
2028-07-16
2028-07-17
2028-07-18
2028-07-19
2028-07-20
2028-07-21
2028-07-22
2028-07-23
2028-07-24
2028-07-25
2028-07-26
2028-07-27
2028-07-28
2028-07-29
2028-07-30
2028-07-31
2028-08-01
2028-08-02
2028-08-03
2028-08-04
2028-08-05
2028-08-06
2028-08-07
2028-08-08
2028-08-09
2028-08-10
2028-08-11
2028-08-12
2028-08-13
2028-08-14
2028-08-15
2028-08-16
2028-08-17
2028-08-18
2028-08-19
2028-08-20
2028-08-21
2028-08-22
2028-08-23
2028-08-24
2028-08-25
2028-08-26
2028-08-27
2028-08-28
2028-08-29
2028-08-30
2028-08-31
2028-09-01
2028-09-02
2028-09-03
2028-09-04
2028-09-05
2028-09-06
2028-09-07
2028-09-08
2028-09-09
2028-09-10
2028-09-11
2028-09-12
2028-09-13
2028-09-14
2028-09-15
2028-09-16
2028-09-17
2028-09-18
2028-09-19
2028-09-20
2028-09-21
2028-09-22
2028-09-23
2028-09-24
2028-09-25
2028-09-26
2028-09-27
2028-09-28
2028-09-29
2028-09-30
2028-10-01
2028-10-02
2028-10-03
2028-10-04
2028-10-05
2028-10-06
2028-10-07
2028-10-08
2028-10-09
2028-10-10
2028-10-11
2028-10-12
2028-10-13
2028-10-14
2028-10-15
2028-10-16
2028-10-17
2028-10-18
2028-10-19
2028-10-20
2028-10-21
2028-10-22
2028-10-23
2028-10-24
2028-10-25
2028-10-26
2028-10-27
2028-10-28
2028-10-29
2028-10-30
2028-10-31
2028-11-01
2028-11-02
2028-11-03
2028-11-04
2028-11-05
2028-11-06
2028-11-07
2028-11-08
2028-11-09
2028-11-10
2028-11-11
2028-11-12
2028-11-13
2028-11-14
2028-11-15
2028-11-16
2028-11-17
2028-11-18
2028-11-19
2028-11-20
2028-11-21
2028-11-22
2028-11-23
2028-11-24
2028-11-25
2028-11-26
2028-11-27
2028-11-28
2028-11-29
2028-11-30
2028-12-01
2028-12-02
2028-12-03
2028-12-04
2028-12-05
2028-12-06
2028-12-07
2028-12-08
2028-12-09
2028-12-10
2028-12-11
2028-12-12
2028-12-13
2028-12-14
2028-12-15
2028-12-16
2028-12-17
2028-12-18
2028-12-19
2028-12-20
2028-12-21
2028-12-22
2028-12-23
2028-12-24
2028-12-25
2028-12-26
2028-12-27
2028-12-28
2028-12-29
2028-12-30
2028-12-31

## do not delete. (hidden)
Hazard Source | Department
Animal
Atmospheric
Biological
Chemical
Cold
Crushing
Electrical
Entanglement
Entrapment
Environmental
Ergonomic
Explosion
Fall from height
Fall same level
Fatigue
Food spoilage
Heat
Housekeeping
Inrush (Water/Mud/Other)
Legislative
Lightening
Lighting
Manual handling
Mechanical damage
Noise / Pressure
Procedure / Process - Lack of
Poisoning
Psychological
Radiation
Sharp Edge/Impliment
Slip
Stored Energy
Struck by / Against
Structural damage
Trip
Untrained / Unskilled / Unqualified
Vibration